## 1.42
Index | Category | Cat # | Requirements | POR | Applicability | RTL 0p0 | RTL 0p5 | RTL 0p8 | RTL 1p0 | Tracking: IP Status | Tracking: SoC Decision | Tracking: Comments | Automation | Tool Rule | Cat Owner | Reference | Requirements Comments | SIP Comments | HIP Comments
2 | Build & Run | 1 | RTL must be uniquified: include all sub-IPs; exclude top-level | Yes | SIP & HIP | Verified | Verified | Verified | Verified | N/A | Not Done | No subIPs used | Auto | 1.2.a | Russ Jackson | Uniquification Methodology
8 | Build & Run | 1 | Use SOC defined BFM versions | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | None used | Auto | 1.8.a | Russ Jackson | RTLTools/IPDS
9 | Build & Run | 1 | Use SOC defined tool versions | Yes | SIP & HIP | Verified | Verified | Verified | Verified | Done | Not Done | Need to veirfy | Auto | 1.9.a | Russ Jackson | Project Tool Versions
10 | Build & Run | 1 | ACE required libraries exist. Separate rtl, test island, and test env libraries | Yes | SIP & HIP | Verified | Verified | Verified | Verified | Done | Not Done | Includes libraries for RTL, no test-island provided, (Integrating IPs will provide collateral for FC) | Auto | 1.10.a | Russ Jackson | Efficient IP Reuse with ACE
11 | Build & Run | 1 | ACE Simluation Environment with reusable integration UDF for verification components and libraries | Yes | SIP & HIP | Verified | Verified | Verified | Verified | Done | Not Done |  | Auto | 1.11.a | Russ Jackson | Efficient IP Reuse with ACE
12 | Build & Run | 1 | ACE support for power aware simulation exists | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | Power intent defined by integrating IP | Auto | 1.12.a | Russ Jackson | RTL Simulation (VCS NLP)
14 | Build & Run | 1 | ACE VCS compilation | Yes | SIP & HIP | Clean | Clean | Clean | Clean | Done | Not Done |  | Auto | 1.14.a | Russ Jackson | Efficient IP Reuse with ACE
15 | Build & Run | 1 | ACE Verdi compilation | Yes | SIP & HIP |  | Clean | Clean | Clean | Done | Not Done |  | Auto | 1.15.a | Russ Jackson | Efficient IP Reuse with ACE |  |  | As applicable, normally not needed
16 | Build & Run | 1 | Integration test list containing reusable tests for SoC integration delivered | Yes | SIP Only |  | Delivered | Delivered | Delivered | N/A | Not Done | Integrating IP will provide reusable tests | Manual | 1.16.a | Russ Jackson | Verification Reference
17 | Build & Run | 1 | IP RTL+IP env must compile, including UPF in the SoC environment and pass basic health tests | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | SoC environment not ready, Integrating IPs would do this. | Manual | 1.17.a | Russ Jackson | RTLTools/IPDS |  |  | HIP not currently converged
19 | Build & Run | 1 | Shared validation libraries (sip_shared_lib) not exported in ACE, must be documented in integration guide | Yes | SIP & HIP | Verified | Verified | Verified | Verified | Done | Not Done | No val libraries used, RTL Libs only are exported | Auto | 1.19.a | Russ Jackson | Efficient IP Reuse with ACE
20 | Build & Run | 1 | Document all workarounds, tie-offs, etc for SOC reuse | Yes | SIP & HIP |  | Documented | Documented | None | N/A | Not Done |  | Manual | 1.20.a | Russ Jackson | RTLTools/IPDS
270 | Build & Run | 1 | IP must follow POR directory structure | Yes | SIP Only | Verified | Verified | Verified | Verified | Done | Not Done |  | Auto | 1.270.a | Russ Jackson | POR Directory Structure
309 | CDC | 2 | QuestaCDC input/output collateral delivered: hierarchical cfm (greybox), cdc_run.log, cdc_settings.rpt, cdc.rpt | Yes | SIP & HIP |  | Verified | Verified | Verified | Done | Not Done | CDC is clean with waivers, CFM will be provided by integrating IP | Auto | <NEED LINK> | Kaushal Dubey | CDC Intelpedia
310 | CDC | 2 | ONDA run is clean | Yes | SIP & HIP |  | Verified | Verified | Verified | Done | Not Done | Clean with waivers | Auto | <NEED LINK> | Kaushal Dubey | CDC Intelpedia
311 | CDC | 2 | ONDA waivers delivered | Yes | SIP & HIP |  | Verified | Verified | Verified | Done | Not Done | ONDA doesn't really support waivers, text file provided describing violations that are waivable | Auto | <NEED LINK> | Kaushal Dubey | CDC Intelpedia
44 | Collage | 3 | coreKit consistent with the RTL | Yes | SIP & HIP | Verified | Verified | Verified | Verified | N/A | Not Done |  | Manual | 3.44.a | Mukesh Mishra | RTL Integration
45 | Collage | 3 | coreKit exists | Yes | SIP & HIP | Verified | Verified | Verified | Verified | N/A | Not Done |  | Auto | 3.45.a | Mukesh Mishra | RTL Integration
46 | Collage | 3 | [ip].coreKit in SoC Context | Yes | SIP & HIP | Verified | Verified | Verified | Verified | N/A | Not Done |  | Manual | 3.46.a | Mukesh Mishra | RTL Integration | Needs Sandbox or SoC, SBX not easily available |  | Understanding is SOC context means with SOC specificied interface versions
48 | Collage | 3 | Collage builder script | Yes | SIP & HIP | Verified | Verified | Verified | Verified | N/A | Not Done |  | Auto | 3.48.a | Mukesh Mishra | RTL Integration
49 | Collage | 3 | Collage summary report | Yes | SIP & HIP | Verified | Verified | Verified | Verified | N/A | Not Done |  | Auto | 3.49.a | Mukesh Mishra | RTL Integration
50 | Collage | 3 | Collage warning report | Yes | SIP & HIP | Verified | Verified | Verified | Verified | N/A | Not Done |  | Auto | 3.50.a | Mukesh Mishra | RTL Integration
51 | Collage | 3 | IP delivered with Collage standard interfaces in CoreKit | Yes | SIP & HIP | Verified | Verified | Verified | Verified | N/A | Not Done |  | Auto | 3.51 (multiple) | Mukesh Mishra | RTL Integration |  |  | SBX flow standardization needed
53 | Collage | 3 | Publish versions of all subIPs and check for SoC level architectural consistency by running Sandbox integration | Yes | SIP & HIP |  |  | Verified | Verified | N/A | Not Done | No subIPs used, sandbox not ready | Auto | 3.53.a | Mukesh Mishra | Sandbox | Methodology being developed
54 | Collage | 3 | Document desitination type (description tag) for all adhoc IP pins (e.g. CCU, PMC, Security, etc.) | No | SIP & HIP |  |  | Verified | Verified | N/A | Not Done |  | Manual | 3.54.a | Mukesh Mishra | RTL Integration
56 | DFt | 4 | [SCAN] - All functional clock gates overriden with fscan_clkungate | Yes | SIP & HIP |  |  | Verified | Verified | Done | Not Done |  | Manual | 4.56.a | Dale March | SoC RTL_DFT_Check
57 | DFt | 4 | [SCAN] - ATPG run and is clean | Yes | SIP & HIP |  |  | Run | 96.7% stuck at; 84.3% at-speed | N/A | Not Done | ATPG will be run by integrating IP | Auto | 4.57.a | Dale March | SoC RTL_DFT_Check
60 | DFt | 4 | [SCAN] - One Scan capture test in GLS is passing for each clock domain | Yes | HIP Only |  |  | Verified | Verified | N/A | Not Done | SCAN flow will be run by integrating IP | Auto | 4.60.a | Dale March | SoC RTL_DFT_Check
61 | DFt | 4 | [SCAN] - Internal component (ctech) MUX added for scan control of all resets and mux output must be active low reset | Yes | SIP & HIP |  |  | Verified | Verified | Done | Not Done |  | Manual | 4.61.a | Dale March | SoC RTL_DFT_Check
62 | DFt | 4 | [BSCAN] - DFT BSDL file for boundary scan delivered | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | BSCAN not applicable | Manual | 4.62.a | Dale March | SoC RTL_DFT_Check
63 | DFt | 4 | [TAP] - Sample trigger SEQUENCE(s)/TEST(s) delivered (for IPs connected to CTBs) | Yes | SIP Only |  |  | Verified | Verified | N/A | Not Done | No TAP | Manual | 4.63.a | Dale March | SoC RTL_DFT_Check
64 | DFt | 4 | RTDR_CTRL | Yes | SIP Only |  |  | Verified | Verified | N/A | Not Done | No TAP | Manual | 4.64.a | Dale March | SoC RTL_DFT_Check |  |  | Need bit more discussion: Do all IP have secure plug in requirement
65 | DFt | 4 | [SCAN] - Coverage reported by DC delivered | Yes | SIP & HIP |  |  | Verified | Verified | N/A | Not Done | SCAN flow will be run by integrating IP | Auto | 4.65.a | Dale March | SoC RTL_DFT_Check
66 | DFt | 4 | [SECURITY] Secure plugin instantiated as part of the IP deliverable | Yes | SIP & HIP |  |  | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Auto | 4.66.a | Dale March | SoC RTL_DFT_Check
67 | DFt | 4 | [SCAN] - Standard scan config file used | Yes | SIP & HIP |  |  | Verified | Verified | N/A | Not Done | SCAN flow will be run by integrating IP | Auto | 4.67.a | Dale March | SoC RTL_DFT_Check
68 | DFt | 4 | [TAP] -sTAPs instantiated where appropriate | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | No TAP | Manual | 4.68.a | Dale March | SoC RTL_DFT_Check
69 | DFt | 4 | TAP IDCODE 32-bit bus correctly defined at IP interface | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | No TAP | Manual | 4.69.a | Dale March | SoC RTL_DFT_Check
70 | DFt | 4 | [TAP] subIP is validated | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | No TAP | Manual | 4.70.a | Dale March | SoC RTL_DFT_Check
71 | DFt | 4 | [TAP] IR/DR information documented in System RDL | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | No TAP | Manual | 4.71.a | Dale March | SoC RTL_DFT_Check
72 | DFt | 4 | [TAP] network is connected | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | No TAP | Manual | 4.72.a | Dale March | SoC RTL_DFT_Check |  |  | Not reviewed
167 | DFt | 4 | [SCAN] - Internally derived clocks pulled to top level with IOSF compliant naming | Yes | SIP & HIP |  |  | Verified | Verified | N/A | Not Done | No internally derived clocks | Manual | 4.167.a | Dale March | SoC RTL_DFT_Check
265 | DFt | 4 | [SCAN] Spyglass-DFT run with SIP_RTL_* release goals using ISAF flow and is clean | Yes | SIP Only |  | Verified | Verified | Clean | N/A | Not Done | Owned by Integrating IP | Auto | 4.265 (multiple) | Dale March | SoC RTL_DFT_Check
315 | DFt | 4 | IP Info file provided (generated with use of ISAF flow) | Yes | SIP Only |  | Verified | Verified | Clean | N/A | Not Done | Owned by Integrating IP | Manual | <NEED LINK> | Dale March | SoC RTL_DFT_Check
79 | Documentation | 5 | Detailed flow description for TAP usage model testing related to IP that cannot be validated at IP level and needs SoC-level testing | Yes | SIP & HIP |  |  | Verified | Clean | N/A | Not Done | No TAP | Manual | 5.79.a | Susann Flowers | Integration Guide
81 | Documentation | 5 | HAS delivered with next milestone content, follows template | Yes | SIP Only | Verified | Verified | Verified | Verified | Done | Not Done | Spec complete | Auto | 5.81.a | Susann Flowers | HAS-EAD
83 | Documentation | 5 | Integration Guide delivered, follows template | Yes | SIP & HIP | Verified | Verified | Verified | Verified | Done | Not Done | IG provided, custom templates | Auto | 5.81.a | Susann Flowers | Integration Guide
86 | Documentation | 5 | Must use the required documentation process | Yes | SIP & HIP | Verified | Verified | Verified | Verified | N/A | Not Done |  | Auto | 5.81.a | Susann Flowers | SIP IP Documentation Process
88 | Documentation | 5 | Product Brief delivered, follows template | Yes | SIP Only | Verified | Verified | Verified | Verified | Not Done | Not Done | Waiver Requested | Auto | 5.81.a | Susann Flowers | Product Brief
90 | Documentation | 5 | Provide following array details for IP: -Array type and # of instances -Functional usage of array (how many bits are used) -Highest functional clock freq of arrays -Array floorplan details -Array security requirements -IP power draw limitations for array testing | Yes | SIP Only | Verified | Verified | Verified | Verified | N/A | Not Done |  | Manual | 5.90.a | Susann Flowers | SIP IP Documentation Process
91 | Documentation | 5 | Release notes exist | Yes | SIP & HIP | Verified | Verified | Verified | Verified | Done | Not Done |  | Auto | 5.91.a | Susann Flowers | Auto Release Notes
93 | Documentation | 5 | Top level port list complete | Yes | SIP & HIP | Verified | Verified | Verified | Verified | Done | Not Done |  | Manual | 5.93.a | Susann Flowers | SIP IP Documentation Process
94 | Documentation | 5 | Verification Reference delivered per HAS requirements, follows template | Yes | SIP & HIP | Verified | Verified | Verified | Verified | N/A | Not Done | Defined by Integrating IP's power validation plan | Auto | 5.81.a | Susann Flowers | Verification Reference
95 | Emulation/FPGA | 6 | RTL and related collaterals must pass Zebu Server and Veloce Emulation Checks | Yes | SIP & HIP |  | Verified | Verified | Verified | Done | Not Done |  | Manual | 6.95.a | Jai Kumar | Emulation-FPGA Friendly Methodology
97 | Emulation/FPGA | 6 | Ensure FW-RTL compatibility in place prior to release (check the FW version) | Yes | SIP Only |  |  | Verified | Verified | N/A | Not Done | No FW | Manual | 6.97.a | Jai Kumar | Emulation CoE
314 | Emulation/FPGA | 6 | RTL and related collaterals must pass FPGA Checks | Yes | SIP Only |  | Verified | Verified | Verified | Done | Not Done |  | Manual | <NEED LINK> | Jai Kumar | Emulation-FPGA Friendly Methodology
98 | FEV | 7 | lec.log and *.rpt or <ip>.report files must exist | Yes | SIP Only |  | Verified | Verified | Verified | Done | Not Done | LEC run | Auto | 7.98.a | Shyama Nath | Equivalency Checking
99 | FEV | 7 | LEC run must be clean at the level of synthesis | Yes | SIP Only |  | Clean | Clean | Clean | Not Done | Not Done | Missing proper rename rules. Request waiver. IP's will run as well before delivering to FC | Auto | 7.99.a | Shyama Nath | Equivalency Checking |  |  | HIP commits to Ckt Vs. RTL FEV pass only by prod.
100 | FEV | 7 | LEC scripts and constraints in the dofile are matching the log file | Yes | SIP Only |  | Verified | Verified | Verified | Not Done | Not Done | Request waiver. IP's will run as well before delivering to FC | Auto | 7.100.a | Shyama Nath | Equivalency Checking |  |  | Less value for HIP and Projects in delivering FEV reports as these are more Ckt Vs. BMOD type reports
101 | FEV | 7 | Set undriven to constant must not be used | Yes | SIP Only |  | Verified | Verified | Verified | Done | Not Done |  | Auto | 7.101.a | Shyama Nath | Equivalency Checking
102 | FEV | 7 | No undriven pins/nets are allowed | Yes | SIP Only |  | Verified | Verified | Verified | Done | Not Done |  | Auto | 7.102.a | Shyama Nath | Equivalency Checking
274 | FEV | 7 | Do not specify "+define+DC" for FEV | Yes | SIP Only |  | Verified | Verified | Verified | Done | Not Done |  | Auto | 7.274.a | Shyama Nath | Equivalency Checking
308 | FEV | 7 | FEV must be run with UPF | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Power intent defined by integrating IP | Auto | <NEED LINK> | Shyama Nath | Equivalency Checking
104 | MCP/FP | 10 | Fishtail passing ( Structural , False Path/ Multy Cycle checks) , waivers file provided | No | SIP Only |  | Verified | Verified | Verified | N/A | Not Done |  | Manual | 10.104.a | Oren Katzir | Timing Exception Checks
1 | Phys Design Enabling | 12 | "current_design" is not used anywhere in the SDC constraints file | Yes | SIP Only |  | Verified | Verified | Verified | Done | Not Done |  | Auto | 12.1.a | Jared Jones | Design Kits
6 | Phys Design Enabling | 12 | Filelist for synthesis in RDT format ( filelist, search paths, defines ) | Yes | SIP & HIP |  | Verified | Verified | Verified | Done | Not Done |  | Auto | 12.6.a | Jared Jones | Design Kits
55 | Phys Design Enabling | 12 | HIPs/EBBs follow EBB methodology - (memories / RF / PLL , LDO) | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done |  | Auto | 12.55 (multiple) | Jared Jones | Design Kits
115 | Phys Design Enabling | 12 | All virtual clocks should be defined in a separate file | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done |  | Auto | 12.115.a | Jared Jones | Design Kits
118 | Phys Design Enabling | 12 | Exceptions among clock groups should be described in a separate file | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Clock definition owned by integrating IP | Auto | 12.118 (multiple) | Jared Jones | Design Kits |  |  | Not applicable to HIP
120 | Phys Design Enabling | 12 | No KITS flow scripts are present in the IP scripts directory | Yes | SIP Only |  | Verified | Verified | Verified | Done | Not Done |  | Auto | 12.120.a | Jared Jones | Design Kits
123 | Phys Design Enabling | 12 | Synthesis block_setup.tcl file contains at least G_DESIGN_NAME and G_LIBRARY_TYPE | Yes | SIP Only |  | Verified | Verified | Verified | Done | Not Done |  | Auto | 12.123.a | Jared Jones | Design Kits
124 | Phys Design Enabling | 12 | Synthesis timing report provided | Yes | SIP Only |  | Within 10% | Meets timing | Meets timing | Done | Not Done | Worst timing paths shown in synthesis reports | Auto | 12.124.a | Jared Jones | Design Kits
275 | Phys Design Enabling | 12 | check_mv_design is run. Free of errors . Warnings are understood/ reviewed | Yes | SIP Only |  | Verified | Verified | Verified | Not Done | Not Done | Flow not ready, Waiver requested | Auto | 12.275.a | Jared Jones | Design Kits
276 | Phys Design Enabling | 12 | All inputs and outputs have IO delay constraints with correct reference clock. Check_design report is clear of unconstrained IO. | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Clock definition owned by integrating IP | Auto | 12.276.a | Jared Jones | Design Kits
277 | Phys Design Enabling | 12 | All constraints (including MCO and DFX) file follow RDT KIT naming conventions. Diff constraints go into appropriate files. | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | No constraints defined, owned by integrating IP | Auto | 12.277.a | Jared Jones | Design Kits
278 | Phys Design Enabling | 12 | Any special strategy for synthesis (e.g. ungroup/flat/-retiming/hierarchical synth/group paths) is documented in integration guide. | Yes | SIP Only |  | Verified | Verified | Verified | Done | Not Done | No special strategy | Manual | 12.278.a | Jared Jones | Design Kits
279 | Phys Design Enabling | 12 | All RTL instantiated clock muxes/architectural clock gates/ clock dividers/clock buffers have corrosponding ctech files and dcszo constraints ( DC size only) | Yes | SIP Only |  | Verified | Verified | Verified | Done | Not Done |  | Auto | 12.279.a | Jared Jones | Design Kits
280 | Phys Design Enabling | 12 | All sequentials are clocked, verified with check_design | Yes | SIP Only |  | Verified | Verified | Verified | Not Done | Not Done | Flow not ready, Waiver requested | Auto | 12.280.a | Jared Jones | Design Kits
281 | Phys Design Enabling | 12 | Scan configuartion files are available for insert_dft to work cleanly. | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | SCAN flow will be run by integrating IP | Auto | 12.281.a | Jared Jones | Design Kits
282 | Phys Design Enabling | 12 | Max leakage power budget defined to be used as constraint during synthesis/APR | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Power intent defined by integrating IP | Manual | 12.282.a | Jared Jones | Design Kits
283 | Phys Design Enabling | 12 | Max power virus number to be used as constraint during IR drop analysis | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Power intent defined by integrating IP | Manual | 12.283.a | Jared Jones | Design Kits
284 | Phys Design Enabling | 12 | Clock name should be a tcl variable and not a hard coded name | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Clock definition owned by integrating IP | Auto | 12.284.a | Jared Jones | Design Kits
285 | Phys Design Enabling | 12 | MCPs / False Paths specification provided | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | No constraints defined, owned by integrating IP | Auto | 12.285.a | Jared Jones | Design Kits
286 | Phys Design Enabling | 12 | Timing critical signals within the IP and at IP boundary | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Clock definition owned by integrating IP | Manual | 12.286.a | Jared Jones | Design Kits
287 | Phys Design Enabling | 12 | I/O are flopped . Specification of IOs which are not flopped to be documented | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Not applicable for SubIPs | Manual | 12.287.a | Jared Jones | Design Kits
288 | Phys Design Enabling | 12 | SDC constraints in RDT format | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | No constraints defined, owned by integrating IP | Manual | 12.288.a | Jared Jones | Design Kits
289 | Phys Design Enabling | 12 | Any logic on the clock path should use clock cells | Yes | SIP Only |  | Verified | Verified | Verified | Done | Not Done |  | Manual | 12.289.a | Jared Jones | Design Kits
291 | Phys Design Enabling | 12 | Gate count numbers are provided | Yes | SIP Only |  | Verified | Verified | Verified | Done | Not Done | Update release notes. | Auto | 12.291.a | Jared Jones | Design Kits |  |  | Not reviewed
292 | Phys Design Enabling | 12 | Cross partition signals changes on each releases. | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Not applicable for SubIPs | Manual | 12.292.a | Jared Jones | Design Kits |  |  | Need more data. Will run it by DFX owner for further clarity
293 | Phys Design Enabling | 12 | Synthesis parameters are set in the synthesis flow . IP synthesized once per process at converged PVT/Guardband | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 12.293.a | Jared Jones | Design Kits
294 | Phys Design Enabling | 12 | Review and waive / accept any Logic on reset | No | SIP Only |  | Verified | Verified | Verified | Done | Not Done | All logic on reset is waived | Auto | 12.294.a | Jared Jones | Design Kits
127 | Power Intent | 13 | UPF 1.0 constructs only in UPF file | Yes | SIP & HIP | Verified | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 13.127.a | Vadivel Ramalingam | SoC Low Power Design
130 | Power Intent | 13 | UPF including sub blocks using load_upf | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 13.130.a | Vadivel Ramalingam | SoC Low Power Design
185 | Power Intent | 13 | Power Management testing (S0ix, save/restore, DVFS etc.) | Yes | SIP & HIP | Review Testplan |  | 100% | 100% | N/A | Not Done | Owned by Integrating IP | Manual | 18.185.a | Vadivel Ramalingam |  |  |  | HIP-only rule
302 | Power Intent | 13 | Power Enable and acknowledgement port names defined | Yes | SIP & HIP | Verified | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 13.302.a | Vadivel Ramalingam | SoC Low Power Design
303 | Power Intent | 13 | HIP/EBB – met lib file quality with respect to Power intent | Yes | HIP Only | Verified | Verified | Verified | Verified | N/A | Not Done | No EBBs | Manual | 13.303.a | Vadivel Ramalingam | SoC Low Power Design
304 | Power Intent | 13 | Any requirements for EBB : RF/ROM/SRAM power enable connections are documented in integration guide. | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | No EBBs | Manual | 13.304.a | Vadivel Ramalingam | SoC Low Power Design
305 | Power Intent | 13 | Any requirements for DELAY cells in power enable chain is documented in integration guide | Yes | HIP Only |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 13.305.a | Vadivel Ramalingam | SoC Low Power Design
306 | Power Intent | 13 | UPF requirements met – Power State Table/Power Domain/Strategies | Yes | SIP & HIP | Verified | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 13.306.a | Vadivel Ramalingam | SoC Low Power Design
307 | Power Intent | 13 | Netlist / post synthesis Spygalss-LP run | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 13.307.a | Vadivel Ramalingam | SoC Low Power Design
312 | Power Intent | 13 | All Power intent Collateral Exists | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Auto | <NEED LINK> | Vadivel Ramalingam | SoC Low Power Design
313 | Power Intent | 13 | RTL free from power-intent logic | Yes | SIP Only |  | Verified | Verified | Verified | Done | Not Done |  | Auto | <NEED LINK> | Vadivel Ramalingam | SoC Low Power Design
131 | Power Lint | 14 | Spyglass-LP for RTL | Yes | SIP & HIP |  | Verified | Verified | Clean | N/A | Not Done | Owned by Integrating IP | Auto | 14.131 (multiple) | Vadivel Ramalingam | SoC RTL Low Power Check
105 | RDL | 11 | [CR] RAL matches RDL, both delivered | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | No Internal Registers | Auto | 11.105 (multiple) | Miles McCoo | Register Management
107 | RDL | 11 | [FUSE+STRAP] RAL matches RDL, both delivered | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | No internal fuses/straps | Auto | 11.105 (multiple) | Miles McCoo | Register Management
111 | RDL | 11 | [CR] RDL quality checks run | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | No RDL | Auto | 11.111.a | Miles McCoo | Register Management | Fishtail being reviewed |  | Not all HIP see applicability at this moment.
112 | RDL | 11 | [FUSE+STRAP] RDL quality checks run | Yes | SIP & HIP |  |  | Verified | Verified | N/A | Not Done | No RDL | Auto | 11.111.a | Miles McCoo | Register Management
168 | RDL | 11 | All IPs should use the 1.0 Fuse Pull Completion Message Format | Yes | SIP Only |  |  | Verified | Verified | N/A | Not Done | No internal fuses/straps | Auto | 17.168.a | Miles McCoo | Fuse Architecture
262 | RDL | 11 | [TAP] RDL quality checks run | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | No TAP | Manual | 11.262.a | Miles McCoo | Register Management
263 | RDL | 11 | [TAP] RDL verified against RTL | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | No TAP | Manual | 11.263.a | Miles McCoo | Register Management
271 | RDL | 11 | [CR] RDL verified against RTL | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | No RDL | Auto | 11.111.a | Miles McCoo | Register Management
272 | RDL | 11 | [FUSE+STRAP] RDL verified against RTL | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | No RDL | Auto | 11.111.a | Miles McCoo | Register Management
273 | RDL | 11 | [TAP] RAL matches RDL, both delivered | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | No TAP | Auto | 11.273.a | Miles McCoo | Register Management
77 | Review | 15 | Commit dates for all IP drops established | Yes | SIP & HIP | Verified | Verified | Verified | Verified | N/A | Not Done |  | Manual | 15.77.a | Oren Katzir, Tom McConnell |  |  |  | Not reviewed
133 | Review | 15 | Functionality coded per HAS, including DFx | Yes | SIP & HIP | HAS0p3 | HAS0p5 | HAS0p8 | 100% coded | Done | Not Done |  | Manual | 15.133.a | Oren Katzir, Tom McConnell |  | Milestone expectations to be reviewed in PLC WG
135 | Review | 15 | All IP Providers are required to run functional GLS or XPROP | Yes | SIP & HIP |  |  | Run | Run | N/A | Not Done | Owned by Integrating IP | Manual | 15.135.a | Oren Katzir, Tom McConnell | RTL Simulation | Milestone expectations to be reviewed in PLC WG
148 | Review | 15 | IP has HSD setup for tracking bugs, PCRs, etc. | Yes | SIP & HIP | Verified | Verified | Verified | Closed | Done | Not Done |  | Auto | 15.148.a | Oren Katzir, Tom McConnell | CSG-SIP HSD (soon HSD-ES) | Milestone expectations to be reviewed in PLC WG
149 | Review | 15 | IP-level RESET waveform review to facilitate integration | Yes | SIP & HIP | Verified | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 15.149.a | Oren Katzir, Tom McConnell |  | Milestone expectations to be reviewed in PLC WG
150 | Review | 15 | NO-INIT signals/paths needed for X-prop and random corrupt modes (for RESET/POWER) are documented/reviewed | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 15.150.a | Oren Katzir, Tom McConnell |  | Milestone expectations to be reviewed in PLC WG
159 | Review | 15 | Major areas of validation RISK from IP provider validation reviewed | Yes | SIP & HIP | Verified | Verified | Verified | Verified | Done | Not Done |  | Manual | 15.159.a | Oren Katzir, Tom McConnell |  | Milestone expectations to be reviewed in PLC WG
160 | Review | 15 | New features and content changes from prior drop reviewed | Yes | SIP & HIP |  |  | Verified | Verified | Done | Not Done |  | Manual | 15.160.a | Oren Katzir, Tom McConnell |  | Milestone expectations to be reviewed in PLC WG
162 | Review | 15 | Placement locations defined for IDV, ODDI, ODDD, CLCP, GLCP | Yes | HIP Only |  | Verified | Verified | Verified | N/A | Not Done |  | Manual | 15.162.a | Oren Katzir, Tom McConnell |  | Milestone expectations to be reviewed in PLC WG
163 | Review | 15 | Review of SoC global connectivity, Param settings, SAI, opcodes, id's, ports, interface & IP integration related | Yes | SIP & HIP | Verified | Verified | Verified | Verified | N/A | Not Done |  | Manual | 15.163.a | Oren Katzir, Tom McConnell |  | Milestone expectations to be reviewed in PLC WG
164 | Review | 15 | Scalability, modularity coded | Yes | SIP Only | Goals established | Goals established | Coded | Coded | Done | Not Done |  | Manual | 15.164.a | Oren Katzir, Tom McConnell |  | Milestone expectations to be reviewed in PLC WG
166 | Review | 15 | Validation Exit Review | Yes | SIP & HIP |  |  |  | Review | Done | Not Done |  | Manual | 15.166.a | Oren Katzir, Tom McConnell |  | Milestone expectations to be reviewed in PLC WG
266 | Review | 15 | IP IRR drop follows naming convention based on DSS | Yes | SIP Only | Review | Review | Review | Review | Done | Not Done |  | Manual | 15.266.a | Oren Katzir, Tom McConnell
268 | Review | 15 | IP is Chassis compliant based on Chassis HAS | Yes | SIP & HIP | Verified | Verified | Verified | Verified | Done | Not Done |  | Manual | 15.268.a | Oren Katzir, Tom McConnell | SoC Chassis Validation
3 | RTL+Lint | 17 | Lintra waiver file names are uniquified with [ip]_ prefix | Yes | SIP & HIP | Verified | Verified | Verified | Verified | Done | Not Done |  | Auto | 17.3.a | Irina Furman | Lintra |  |  | VCS only
4 | RTL+Lint | 17 | Lintra waiver ID names are uniquified | Yes | SIP & HIP | Verified | Verified | Verified | Verified | Done | Not Done |  | Auto | 17.4.a | Irina Furman | Lintra
47 | RTL+Lint | 17 | Clocks and resets are defined only in interfaces | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done |  | Auto | 17.47.a | Irina Furman | Lintra
170 | RTL+Lint | 17 | Lintra FPGA friendliness | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | No rule exists | Auto | 17.170.a | Irina Furman | Lintra | Milestone expectations to be reviewed in PLC WG
171 | RTL+Lint | 17 | Lintra reports are clean – no Fatals and Errors | Yes | SIP & HIP | Verified | Verified | Verified | Verified | Done | Not Done |  | Auto | 17.171.a | Irina Furman | Lintra | Milestone expectations to be reviewed in PLC WG
172 | RTL+Lint | 17 | Lintra waiver are available | Yes | SIP & HIP | Verified | Verified | Verified | Verified | Done | Not Done |  | Auto | 17.172.a | Irina Furman | Lintra | Milestone expectations to be reviewed in PLC WG
173 | RTL+Lint | 17 | Lintra waivers apply only to files in the IP | Yes | SIP & HIP | Verified | Verified | Verified | Verified | Done | Not Done |  | Auto | 17.173.a | Irina Furman | Lintra | Milestone expectations to be reviewed in PLC WG
316 | RTL+Lint | 17 | RTL follows CTECH coding methodology | Yes | SIP Only | Verified | Verified | Verified | Verified | Done | Not Done |  | Auto | <NEED LINK> | Irina Furman | Lintra
295 | Security | 18 | Security Risk Assessment (SRA) is completed | Yes | SIP & HIP | Verified | Verified | Verified | Verified | Done | Not Done |  | Manual | 18.295.a | Truc Nguyen | Security Risk Assessment
296 | Security | 18 | SRA results have been added to the security section in the IP’s Architecture Specification (HAS) | Yes | SIP & HIP | Verified | Verified | Verified | Verified | Done | Not Done |  | Manual | 18.296.a | Truc Nguyen | HAS-EAD
297 | Security | 18 | The IP architecture and design conforms to the SDL policies | Yes | SIP & HIP | Verified | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 18.297.a | Truc Nguyen | SDL Policies
298 | Security | 18 | Architecture security review completed according to the SDL activities listed from the SRA for S1 | Yes | SIP & HIP | Verified | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 18.298.a | Truc Nguyen | SDL Activitity: S1
299 | Security | 18 | The security section in the IP architecture specification (EAD or HAS) updated with integration collateral | Yes | SIP & HIP |  |  | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 18.299.a | Truc Nguyen | Document Templates
300 | Security | 18 | Design security review completed according to the SDL activities listed from the SRA for S2 | Yes | SIP & HIP |  |  | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 18.300.a | Truc Nguyen | SDL Activitity: S2
301 | Security | 18 | The IP security test plan is completed and executed for S3 | Yes | SIP & HIP |  |  |  | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 18.301.a | Truc Nguyen | SDL Activitity: S3
179 | Simulation | 19 | CREG: Control Registers verification | Yes | SIP & HIP | Review Testplan | Basic Access | 100% | 100% | N/A | Not Done | No Registers | Auto | 19.179.a | Mohamed Elmalaki | Verification Reference | Milestone expectations to be reviewed in PLC WG
180 | Simulation | 19 | Delivered verification collateral conforms to guidelines in ACE Reuse Checklist | Yes | SIP Only | Verified | Verified | Verified | Verified | N/A | Not Done | PGCB does not directly deliver reusable val collateral, see Chassis VIP | Auto | 19.180 (multiple) | Mohamed Elmalaki | Efficient IP Reuse with ACE
181 | Simulation | 19 | DFT: Design for Test features verification | Yes | SIP & HIP | Review Testplan | 50% | 80% | 100% | Done | Not Done |  | Auto | 19.181.a | Mohamed Elmalaki | VCS FAQ
182 | Simulation | 19 | DFV: Design for Validation features verification | Yes | SIP & HIP | Review Testplan | 50% | 80% | 100% | Done | Not Done |  | Auto | 19.182.a | Mohamed Elmalaki | VCS FAQ | Milestone expectations to be reviewed in PLC WG
183 | Simulation | 19 | Plan and implement a coverage plan (functional/code) | Yes | SIP & HIP |  |  | 80% functional coverage | 100% functional coverage | Done | Not Done |  | Auto | 19.183.a | Mohamed Elmalaki | VCS FAQ | Milestone expectations to be reviewed in PLC WG |  | HIP-only rule
184 | Simulation | 19 | FUSE: IP Fuses verification | Yes | SIP & HIP | Review Testplan | Fuse Download, defaults | 100% | 100% | N/A | Not Done | No fuses | Auto | 19.184.a | Mohamed Elmalaki | VCS FAQ | Milestone expectations to be reviewed in PLC WG
187 | Simulation | 19 | RESET: IP Reset Verification | Yes | SIP & HIP | Review Testplan | Basic Reset (no injections) | 100% | 100% | Done | Not Done |  | Auto | 19.187.a | Mohamed Elmalaki | VCS FAQ | Milestone expectations to be reviewed in PLC WG
191 | Simulation | 19 | VCS-NLP power simulation | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | Power intent defined by integrating IP | Manual | 19.191.a | Mohamed Elmalaki | RTL Simulation (VCS NLP) | Milestone expectations to be reviewed in PLC WG
196 | SV TB | 20 | Coverage coded | Yes | SIP Only |  | 10% coverage coded | 100% coverage coded | 100% coverage coded | Done | Not Done |  | Auto | 20.196.a | Hassan Shehab | SVTB | Milestone expectations to be reviewed in PLC WG
197 | SV TB | 20 | Delivered verification collateral conforms to guidelines in OVM VIP Conformance Checklist | Yes | SIP Only | Verified | Verified | Verified | Verified | N/A | Not Done | PGCB does not directly deliver reusable val collateral, see Chassis VIP | Manual | 20.197.a | Hassan Shehab | OVM Compliance | Milestone expectations to be reviewed in PLC WG
198 | SV TB | 20 | Delivered verification collateral conforms to guidelines in Saola Compliance Checklist | Yes | SIP Only | Verified | Verified | Verified | Verified | N/A | Not Done | PGCB does not directly deliver reusable val collateral, see Chassis VIP | Manual | 20.198.a | Hassan Shehab | Saola Compliance
199 | SV TB | 20 | Delivered verification collateral conforms to guidelines in Test Island Compliance Checklist | Yes | SIP Only | Verified | Verified | Verified | Verified | N/A | Not Done | PGCB does not directly deliver reusable val collateral, see Chassis VIP | Manual | 20.199.a | Hassan Shehab | Test Island Compliance
200 | SV TB | 20 | Disallow forces except in test bench | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | PGCB does not directly deliver reusable val collateral, see Chassis VIP | Manual | 20.200.a | Hassan Shehab | SVTB
211 | SV TB | 20 | Test list with integration power stress tests for POWER metrics | Yes | SIP Only |  |  | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Auto | 20.211.a | Hassan Shehab | SVTB
212 | SV TB | 20 | Test list with integration tests for USE CASE testing delivered | Yes | SIP Only |  |  | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Auto | 20.212.a | Hassan Shehab | SVTB | IPFuseCheck.pl script
213 | SV TB | 20 | Test list with integration tests for use in PERFORMANCE analysis delivered | Yes | SIP Only |  |  | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Auto | 20.213.a | Hassan Shehab | SVTB |  |  | Need more information
214 | SV TB | 20 | IP-level test coded | Yes | SIP Only |  | Per HAS0p5 | Per HAS0p8 | Per HAS1p0 | Done | Not Done |  | Auto | 20.214.a | Hassan Shehab | SVTB
215 | SV TB | 20 | IP-level tests passing | Yes | SIP Only |  | One test passing | 85% passing of planned | 100% passing of planned | Done | Not Done |  | Auto | 20.215.a | Hassan Shehab | SVTB
217 | SV TB | 20 | RAL adaptor sequences exist | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | No registers | Auto | 20.217.a | Hassan Shehab | SVTB
221 | SV TB | 20 | Reusable TEST ISLAND delivered with no # delays | Yes | SIP Only | Verified | Verified | Verified | Verified | N/A | Not Done | PGCB does not directly deliver reusable val collateral, see Chassis VIP | Auto | 20.221.a | Hassan Shehab | SVTB
226 | SV TB | 20 | Stand alone integration test (data flow, connectivity) | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | PGCB does not directly deliver reusable val collateral, see Chassis VIP | Auto | 20.226.a | Hassan Shehab | SVTB
227 | SV TB | 20 | Test island does not have hard coded paths | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | PGCB does not directly deliver reusable val collateral, see Chassis VIP | Auto | 20.227.a | Hassan Shehab | SVTB | IP3 activity
228 | SV TB | 20 | Test island does not use hard code hierarchical refs | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | PGCB does not directly deliver reusable val collateral, see Chassis VIP | Auto | 20.228.a | Hassan Shehab | SVTB
231 | SV TB | 20 | The IP should have a re-usable scoreboard (Runtime or Post-Processing)” | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | PGCB does not directly deliver reusable val collateral, see Chassis VIP | Auto | 20.231.a | Hassan Shehab | SVTB
232 | SV TB | 20 | VIP scoreboards, assertions | Yes | SIP Only |  |  | 90% checks enabled | 100% checks enabled | N/A | Not Done | PGCB does not directly deliver reusable val collateral, see Chassis VIP | Manual | 20.232.a | Hassan Shehab | SVTB
267 | SV TB | 20 | All the error waivers and disable calls are in one place | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | None needed | Auto | 20.267.a | Hassan Shehab | SVTB
176 | VISA | 21 | Clocks should not be added to the network as data to the network. If it is a must, then it must be noted that the clock will only give an indication that it is alive or dead and cannot be used for measuring frequency. The clock will be marked as a false path. | Yes | SIP Only |  | Verified | Verified | Verified | Done | Not Done | No clocks in VISA | Manual | 4.176.a | Amitai Irron | VISA IT Standards Clarification | Milestone expectations to be reviewed in PLC WG
233 | VISA | 21 | All signals exposing fuse data must be at a minimum marked Red or not added to the network. | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | No Fuses | Manual | 21.233.a | Amitai Irron | VISA IT Standards Clarification
234 | VISA | 21 | Confirm IP identifiers (SRCID, etc.) with assignment | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done |  | Manual | 21.234.a | Amitai Irron | VISA IT Standards Clarification |  |  | Need more information
235 | VISA | 21 | Provide Makefile to run the VISA flow and validation | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Auto | 21.235 (multiple) | Amitai Irron | VISA IT Standards Clarification
237 | VISA | 21 | Please add below ULM flops to the SR list in IP's upf file: visa_unit_mux_s/deserializer/all_cr | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 21.237.a | Amitai Irron | VISA IT Standards Clarification
238 | VISA | 21 | Two output lanes per ULM, ie. A single input lane can only go to a maximum of 2 output lanes | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Auto | 21.238.a | Amitai Irron | VISA IT Standards Clarification
239 | VISA | 21 | Due to the PGD ULM signals which coming out from PGD to AON, these signals should be isolated: (/visa_unit_mux_s/ss_clk_out, /visa_unit_mux_s/xbar_ss_clk_out, /visa_unit_mux_s/xbar_out, /visa_unit_mux_s/lane_out) | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 21.239.a | Amitai Irron | VISA IT Standards Clarification
240 | VISA | 21 | Do not gate the visa serial clock when asserting SLEEP signal. | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 21.240.a | Amitai Irron | VISA IT Standards Clarification
241 | VISA | 21 | Override the reset when asserting/deasserting SLEEP signal. No need to synchronous the visa reset as the VISA requires asynchronous reset assertion/deassertion. i.e. to insert AND gate to override the VISA reset signal (visa_resetb) with PGCB’s forcerst_b, and set_false_path that overriding path (from PGCB’s forcerst_b to that AND gate). | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 21.241.a | Amitai Irron | VISA IT Standards Clarification
242 | VISA | 21 | VISA probe budget based on IP type and area matrix | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 21.242.a | Amitai Irron | VISA IT Standards Clarification |  |  | Not reviewed
243 | VISA | 21 | Check in the <IP>/tools/visa/<IP>.sig | Yes | SIP Only |  | Verified | Verified | Verified | Done | Not Done |  | Auto | 21.243 (multiple) | Amitai Irron | VISA IT Standards Clarification |  |  | for 0p0/0p5 history says it is hard to meet. But 0p8 is a good commit date
244 | VISA | 21 | Control signal for visa state retention. flop will be tied to IP functional’s sleep signal. | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 21.244.a | Amitai Irron | VISA IT Standards Clarification
245 | VISA | 21 | Ensure visa_validate is reusable, and tests are passing | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 21.245.a | Amitai Irron | VISA IT Standards Clarification
246 | VISA | 21 | Follow IOSF naming convention for VISA interface signals | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 21.246.a | Amitai Irron | VISA IT Standards Clarification |  |  | Some exceptions may be there e.g. OPI. These need to be closed between HIP, SIP and SOC owners
247 | VISA | 21 | Reusable connectivity test (connectivity from DFX security plugin to each VISA ULM) | Yes | SIP Only |  |  | Delivered | Delivered | N/A | Not Done | Owned by Integrating IP | Manual | 18.247.a | Amitai Irron | VISA IT
248 | VISA | 21 | Max 16 bits per small IP, 32 bits per med IP, 64 bits for large IP | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Auto | 21.248.a | Amitai Irron | VISA IT Standards Clarification
249 | VISA | 21 | Max 512 bits per ULM | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Auto | 21.249.a | Amitai Irron | VISA IT Standards Clarification
250 | VISA | 21 | No power domain mixing per output lane per ULM | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 21.250.a | Amitai Irron | VISA IT Standards Clarification
251 | VISA | 21 | No visa on array dft'd stuff (not every bit of a large structure - register file and srams) | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 21.251.a | Amitai Irron | VISA IT Standards Clarification
252 | VISA | 21 | No visa xbar at ULM - review with visa architects if needed | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Auto | 21.252.a | Amitai Irron | VISA IT Standards Clarification
253 | VISA | 21 | Review perfmon compatibility with visa architects | Yes | SIP Only |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 21.253.a | Amitai Irron | VISA IT Standards Clarification
254 | VISA | 21 | ULM which resides in a power gated domain will need to have state retention flops (SR). | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 21.254.a | Amitai Irron | VISA IT Standards Clarification
255 | VISA | 21 | ULMs should not contain signals from other IPs. If a signal (or set of signals) must be used, they must be flopped (to meet timing) before they enter the network. All data inputs to the ULM must be driven from sequentials inside the unit itself | Yes | SIP & HIP |  | Verified | Verified | Verified | N/A | Not Done | Owned by Integrating IP | Manual | 21.255.a | Amitai Irron | VISA IT Standards Clarification
256 | VISA | 21 | Understand and comprehend the Post-Si validation cost of not having visibility on the proper signals through Visa | Yes | SIP & HIP |  | Verified | Verified | Verified | Done | Not Done |  | Manual | 21.256.a | Amitai Irron | VISA IT Standards Clarification
257 | VISA | 21 | Understand and comprehend the potential explosion of back end place, route and power effort due to poorly chosen Visa coverage | Yes | SIP & HIP |  | Verified | Verified | Verified | Done | Not Done |  | Manual | 21.257.a | Amitai Irron | VISA IT Standards Clarification
258 | VISA | 21 | Understand and comprehend timing convergence, false path disabling, power domain handling, etc. complexity of Visa | Yes | SIP & HIP |  | Verified | Verified | Verified | Done | Not Done |  | Manual | 21.258.a | Amitai Irron | VISA IT Standards Clarification

## Categories
Category | Category # | Number of Standards | Owner | Org Affiliation
Build & Run | 1 | 13 | Russ Jackson | DTS - CDS - SOC FE DA
CDC | 2 | 3 | Kaushal Dubey | DTS - CDS - SOC FE DA
Collage | 3 | 9 | Mukesh Mishra | IPG EIG Chassis Automation
DFt | 4 | 18 | Dale March | iDGz Chipset Manufacturing Capabilities
Documentation | 5 | 9 | Susann Flowers | IPG EIG Soft IP Customer Support
Emulation/FPGA | 6 | 3 | Jai Kumar | DTS Virtual Plaform Center
FEV | 7 | 7 | Shyama Nath | CCDO DA
Formal Property | 8 | 0 | Erik Seligman | DTS ASVS FV COE
Functional Qualification | 9 | 0 | (TBD) | (TBD)
MCP/FP | 10 | 1 | Oren Katzir | IPG EIG IP Integration
RDL | 11 | 10 | Miles McCoo | DTS CDS FE Logic Simulation
Phys Design Enabling | 12 | 27 | Jared Jones | FCDC Implementation and Integration
Power Intent | 13 | 11 | Vadivel Ramalingam | DTS - CDS - SOC DA BA
Power Lint | 14 | 1 | Vadivel Ramalingam | DTS - CDS - SOC DA BA
Review | 15 | 14 | Oren Katzir, Tom McConnell | CSG SoC; CSG-SIP Technology Office
RTL Version Control | 16 | 0 | Greg Logan | DTS - CDS - SOC FE DA
RTL+Lint | 17 | 8 | Irina Furman | DTS CDS FE RTL MMDC
Security | 18 | 7 | Truc Nguyen | PEG SVE SeCOE
Simulation | 19 | 8 | Mohamed Elmalaki | PEG CSG Soft IP
SV TB | 20 | 18 | Hassan Shehab | DTS - CDS - SOC FE DA
VISA | 21 | 4 | Amitai Irron | DTS - ASVS - SV - Manual Debug
Back End Readiness | 22 | 0 | Said Boumaraf | IPG HIP Methodology

## Revisions
Version | Date | Modified by | Comments | IPDS Ratified Changes # | HSD-ES
0.00 | WW27.4 2013 | tmcconne | Initial version
0.01 | WW27.0 2013 | tmcconne | Added VICEE
0.02 | WW27.0 2013 | tmcconne | Includes all (current) source documents. High-level intial judgement on automation, category, etc.
0.03 | WW27.0 2013 | tmcconne | Added Excel title
0.04 | WW29.1 2013 | tmcconne | Added sub-categories
0.05 | WW29.2 2013 | tmcconne | Added POR tools.
0.05 | WW30.0 2013 | tmcconne | Added DNV RTL0p5 criteria
0.06 | WW30.0 2013 | tmcconne | Added categories and category owners
0.07 | WW30.4 2013 | tmcconne | Minor changes, versioned for email
0.08 | WW30.4 2013 | tmcconne | Result of Dungeon, Day 1.
0.08 | WW30.4 2013 | tmcconne | Some rewording.
0.08 | WW30.4 2013 | tmcconne | Redundancies identified through R0p5
0.08 | WW30.4 2013 | tmcconne | New categories
0.09 | WW30.4 2013 | tmcconne | Updated Revision page
0.09 | WW30.4 2013 | tmcconne | Added maturity columns
0.09 | WW30.4 2013 | tmcconne | Removed redundancies
0.09 | WW30.4 2013 | tmcconne | Implementes some of "Dungeon, Day 1" recommended changes
0.09 | WW30.4 2013 | tmcconne | Began work on Rev 0.10
0.10 | WW30.5 2013 | tmcconne | Result of Dungeon, Day 2
0.11 | WW30.5 2013 | tmcconne | Removed rest of "obvious" redundancies.
0.12 | WW31.1 2013 | Mike Smith | Collapsed VICEE requirements
0.13 | WW31.2 2013 | tmcconne | Minor changes, versioned for email
0.14 | WW31.3 2013 | tmcconne | VISA category cleanup
0.15 | WW31.3 2013 | tmcconne | Removed some clutter (old columns, mostly), reorganized for production
1.00 | WW31.3 2013 | tmcconne | Removed older revisions for production release
1.00 | WW31.3 2013 | tmcconne | Filled in blank VISA milestones
1.01 | WW31.5 2013 | tmcconne | Updated Category owners
1.02 | WW32.1 2013 | tmcconne | Added #rules and org affiliation to categories
1.02 | WW32.2 2013 | tmcconne | Filled in org affiliations
1.02 | WW32.3 2013 | tmcconne | Added "Tracking" columns
1.02 | WW32.3 2013 | tmcconne | Replaced spaces with underscores in file name for UNIX compatibility
1.02 | WW32.3 2013 | tmcconne | Added IP Status pull-down to enforce specific values
1.02 | WW32.3 2013 | tmcconne | Removed "Collateral File" column. Doesn't seem useful (need reference instead)
1.02 | WW32.4 2013 | tmcconne | Added "Rule Status" to support project-specific rules
1.02 | WW32.4 2013 | tmcconne | Protected the stable (converged) requirements, allow changes only to Tracking and additional project rules
1.03 | WW32.4 2013 | tmcconne | Added "Recommended" to Rule Status
1.03 | WW32.5 2013 | tmcconne | Removed protection, can't filter or hide columns which makes it hard to use.
1.03(DNV) | WW32.5 2013 | tmcconne | Version released to DNV for IP Requirements tracking pilot
1.04 | WW33.2 2013 | tmcconne | Added colorization to tracking information
1.04 | WW34.1 2013 | tmcconne | Added Index to clearly identify rules
1.04 | WW34.1 2013 | tmcconne | Added colorization to Rule Status
1.05 | WW34.2 2013 | tmcconne | Removed Rule Status
1.05 | WW34.2 2013 | tmcconne | Removed Source columns
1.05 | WW34.2 2013 | tmcconne | Removed Rel 1.03
1.05 | WW34.2 2013 | tmcconne | Removed blank rows below converged requirements
1.05 | WW34.2 2013 | tmcconne | (This happened in 1.04, I think) Cleaned up some rule descriptions, especially in CDC, for better understanding
1.06 | WW34.2 2013 | tmcconne | Updated "Check ETA", some check tools and some requirement categories based on Essam and Oren
1.06 | WW34.2 2013 | tmcconne | Updated VISA-> RTL+Lint and ZQA-> SBX per Essam and Oren
1.07 | WW34.3 2013 | tmcconne | Updated ZQA date for VISA xbar
1.08 | WW34.4 2013 | tmcconne | Updated Check, Tool and Check ETA based on Essam and Oren
1.09 | WW34.5 2013 | tmcconne | Custom Design Integration combined with Phys Design. Only rule 55 affected.
1.09 | WW34.5 2013 | tmcconne | Updated Category owners
1.10 | WW34.5 2013 | tmcconne | Removed Functional Qualification category owner (now TBD)
1.11 | WW37.4 2013 | tmcconne | Removed tracking revision
1.11 | WW37.4 2013 | tmcconne | Refined Tracking values, initial value is now "Not Done"
1.11 | WW37.4 2013 | tmcconne | Wrap the text in requirements so the standards are always fully visible
1.12 | WW38.3 2013 | tmcconne | Removed "Exception Request" and "Waive"
1.13 | WW39.3 2013 | tmcconne | Added "Tracking: SoC Decision" and updated Tracking tab
1.13 | WW39.3 2013 | tmcconne | Updated text in Collage category based on WW38'13 IPDS WG update
1.13 | WW39.3 2013 | tmcconne | Updated RTL+Lint requirements based on WW39'13 IPDS WG update
1.14 | WW39.3 2013 | tmcconne | Changed "Nebulon" category to "RDL"
1.14 | WW39.3 2013 | tmcconne | Index 167: (internal clocks) moved to DFt | 4
1.14 | WW39.3 2013 | tmcconne | Removed Index 174: (comments) | 3
1.14 | WW39.3 2013 | tmcconne | Removed Index 177: (VISA) | 3
1.14 | WW39.3 2013 | tmcconne | Removed Index 178: (VISA) | 3
1.15 | WW41.3 2013 | tmcconne | Added Index 259, 260, 261: various "no CDC warnings" | 1
1.15 | WW41.3 2013 | tmcconne | Remove Index 52: Collage, deliver collage subsystem | 2
1.15 | WW41.3 2013 | tmcconne | Index 77 (commit dates): Move to Review | 5
1.15 | WW41.3 2013 | tmcconne | Index 84 (transfer through IRR): Move to Review | 5
1.15 | WW41.3 2013 | tmcconne | Added "Requirements Comments" column to capture things like POR vs. proposed | 8
1.15 | WW41.3 2013 | tmcconne | Index 95: emubuild is a proposed tool, not yet POR (DNV pilot) | 8
1.15 | WW41.3 2013 | tmcconne | Index 176: (clocks as data) moved to DFt
1.16 | WW41.3 2013 | tmcconne | Index 243: Change file name to <IP>/tools/visa/<IP>.sig | 6
1.16 | WW41.3 2013 | tmcconne | Removed index 236 | 7
1.17 | WW42.3 2013 | tmcconne | Added links to "Tool", "Exists?" and "Reference" columns
1.18 | WW43.2 2013 | tmcconne | Removed Index 161: (Review) | 9
1.18 | WW43.2 2013 | tmcconne | Removed Index 134: (Review) | 9
1.18 | WW43.2 2013 | tmcconne | Added "Review -> Protect Sheet" to prevent modifying requirements
1.19 | WW43.3 2013 | tmcconne | Updated wording for Fishtail, Index 104. POR being reviewed | 20
1.19 | WW43.3 2013 | tmcconne | Index 132: Fixed spelling
1.19 | WW43.3 2013 | tmcconne | Changed "Exists?" column name to "Tool Rule"
1.19 | WW43.3 2013 | tmcconne | Index 148: Improved "HSD" wording
1.19 | WW43.3 2013 | tmcconne | Updated all RDL rules (removed Index 106, 108, 109, 110, 113; added Index 259-263) | 10 through 19
1.19 | WW43.3 2013 | tmcconne | Index 104: Report exists at RTL0p5, clean starting with RTL0p7 | 21
1.19 | WW43.3 2013 | tmcconne | Added HIP columns, based on SIP-HIP Sept. 25 review
1.20 | WW43.4 2013 | tmcconne | Unlock Tracking Comments column
1.21 | WW43.4 2013 | tmcconne | Index 131: Update Power Lint, Spyglass-LP Reference link
1.22 | WW43.4 2013 | tmcconne | Removed Index 175: No longer generally applicable with central CTECH library | 27
1.22 | WW43.4 2013 | tmcconne | Removed index 73, 74, 75, 76, 78, 80, 82, 85, 87, 89, 92: Redundant per Susann Flowers
1.22 | WW43.4 2013 | tmcconne | Index 127: Changed requirement based on IPDS WG decision | 25
1.22 | WW43.4 2013 | tmcconne | Index 47: Moved to RTL+Lint | 22
1.22 | WW43.4 2013 | tmcconne | Index 46: Added comment about SBX not being available | 23
1.22 | WW43.4 2013 | tmcconne | Index 54: Added comment, not currently POR | 24
1.22 | WW43.4 2013 | tmcconne | Added Index 264: HIP-only rule | 26
1.23 | WW43.4 2013 | tmcconne | Added "HSD-ES" column to Revisions
1.23 | WW43.4 2013 | tmcconne | Removed "RTL: BXT will have no high security fuses" from "Further review" |  | 1012053111
1.23 | WW43.4 2013 | tmcconne | Added "Spyglass DFT" as a requirement |  | 1012740574
1.23 | WW43.5 2013 | tmcconne | Change "FUSE" to "FUSE+STRAP" for RDL
1.23 | WW44.1 2013 | tmcconne | Index 131: Update Spyglass-LP Reference link to Spyglass-LP training materials
1.23 | WW46.1 2013 | tmcconne | Added "Next Rule #" to Tracking tab to keep track of new rule numbers
1.23 | WW46.1 2013 | tmcconne | Added Index 266: IP follows naming convention based on DSS | 28
1.23 | WW46.1 2013 | tmcconne | Added "HIP Comments" column
1.23 | WW46.1 2013 | tmcconne | Updated "HIP" column to reflect "IP_Requirements_1 20_updated" review from HIP
1.24 | WW46.5 2013 | tmcconne | Remove standards #195, #201, #218-219, #194, #232, #192-193, #202-210, #216, #220, #222-225, #229-230 | 29
1.24 | WW46.5 2013 | tmcconne | Index 231: Improved re-usable scoreboard wording | 30
1.24 | WW46.5 2013 | tmcconne | Added Index 267: waivers and disable calls in one place | 31
1.25 | WW47.1 2013 | tmcconne | Fixed broken link to non-existent file
1.26 | WW47.1 2013 | tmcconne | Protect requirements tab
1.27 | WW47.3 2013 | tmcconne | Updated ZQA link to new zircon.fm.intel.com site
1.27 | WW47.3 2013 | tmcconne | Index 131, 265: Updated Spyglass Reference links per Tho Nguyen
1.27 | WW47.4 2013 | tmcconne | Added "Soft IP" to "Requirements" and "Requirements Comments" columns
1.27 | WW47.4 2013 | tmcconne | Renamed "Check" column to "Automation"
1.27 | WW47.4 2013 | tmcconne | Renamed "Check ETA" to "Tool ETA"
1.27 | WW47.4 2013 | tmcconne | Removed links in Tracking columns. Sharepoint support in Excel complicated the link
1.27 | WW47.4 2013 | tmcconne | Renamed "Tracking" sheet to "Tracking, Field Values" to better identify data
1.28 | WW47.5 2013 | tmcconne | Updated Documentation reference links
1.29 | WW48.1 2013 | tmcconne | Add "Applicability" column for "SIP Only", "HIP Only", "SIP & HIP"
1.29 | WW48.1 2013 | tmcconne | Removed "HIP" column
1.29 | WW48.1 2013 | tmcconne | Added "SIP Comments" column
1.29 | WW48.1 2013 | tmcconne | Renamed "Soft IP Requirements" back to "Requirements"
1.29 | WW48.1 2013 | tmcconne | Removed Index 132: All general collateral, quality and reuse expectations | 34
1.29 | WW48.1 2013 | tmcconne | Replaced Index 137-147 with new Index 268: "IP is Chassis compliant based on Chassis HAS" | 35
1.29 | WW48.1 2013 | tmcconne | Replaced Index 152-158 with new Index 269: "Review IP-level testing: Documentation and collateral expectations" | 36
1.29 | WW48.1 2013 | tmcconne | Added "Security" category, with Truc Nguyen as the owner
1.29 | WW48.1 2013 | tmcconne | Move Index #165, 189, 247 to Security | 33
1.29 | WW48.1 2013 | tmcconne | Use "Verified" in place of: Provided, Complete, Pass, Delivered, Reviewed, Compiles, Coded, Included, Exists
1.29 | WW48.1 2013 | tmcconne | Added Index 270 to Build & Run: IP must follow POR directory structure | 32
1.29 | WW48.1 2013 | tmcconne | Replaced Automation of "Partial" with "Manual"
1.29 | WW48.1 2013 | tmcconne | Replaced Automation of "Auto" with "Future" if there is no rule listed
1.30 | WW50.2 2013 | tmcconne | Fixed duplicate Index entries: Build & Run 258 -> 270
1.30 | WW50.2 2013 | tmcconne | Fixed duplicate Index entries: RDL 259 -> 271
1.30 | WW50.2 2013 | tmcconne | Fixed duplicate Index entries: RDL 260 -> 272
1.30 | WW50.2 2013 | tmcconne | Fixed duplicate Index entries: RDL 261 -> 273
1.30 | WW50.2 2013 | tmcconne | Move standards #1 and #6 to Physical Design category. | 37
1.30 | WW50.2 2013 | tmcconne | Move standards #3 and #4 to RTL+Lint category. | 38
1.30 | WW50.2 2013 | tmcconne | Combine standards #2 and #7 (Remove #7)– Reword for clarity | 39
1.30 | WW50.2 2013 | tmcconne | Move standard #5 to CDC category. Reword to emphasize process library cells used for CTECH | 40
1.30 | WW50.2 2013 | tmcconne | In standard #98, add requirement for providing lec.log file (in addition to providing LEC reports). | 41
1.30 | WW50.4 2013 | tmcconne | Added Index #274: Do not specify "+define+DC" for FEV | 42
1.30 | WW50.4 2013 | tmcconne | Index #131: Add "for RTL" | 43
1.31 | WW50.5 2013 | tmcconne | Replaced "Tool" of "Collect" with "Other"
1.31 | WW50.5 2013 | tmcconne | Index #168: (Fuse Pull Completion Message format) is “SIP Only”
1.31 | WW50.5 2013 | tmcconne | Index #264 (Power-aware .lib) is HIP-only
1.31 | WW50.5 2013 | tmcconne | Index #77 (commit dates) is an IP3 activity. Expect to remove this in a future release.
1.32 | WW51.1 2013 | tmcconne | Changed Q3'13 with Q4'13 in Tool ETA
1.32 | WW51.1 2013 | tmcconne | Removed all Tool ETA for Auto rules that have a Tool Rule
1.32 | WW51.1 2013 | tmcconne | Removed Tool Rule of "??"
1.32 | WW51.1 2013 | tmcconne | Froze "Index", "Category" and "Requirements" columns to help with usability
1.32 | WW51.1 2013 | tmcconne | Changed "RTL+Lint" category owner to Irina Furman
1.33 | WW51.1 2013 | tmcconne | Removed filter on rules
1.34 | WW51.5 2013 | tmcconne | Added Phys Design standards, Index #275-294 | 44-63
1.34 | WW51.5 2013 | tmcconne | Removed Index #114 | 64
1.34 | WW51.5 2013 | tmcconne | Removed Index #116 | 65
1.34 | WW51.5 2013 | tmcconne | Removed Index #117 | 66
1.34 | WW51.5 2013 | tmcconne | Removed Index #119 | 67
1.34 | WW51.5 2013 | tmcconne | Removed Index #121 | 68
1.34 | WW51.5 2013 | tmcconne | Removed Index #122 | 69
1.34 | WW51.5 2013 | tmcconne | Removed Index #125 | 70
1.34 | WW51.5 2013 | tmcconne | Removed Index #126 | 71
1.34 | WW51.5 2013 | tmcconne | Index #55: Improved wording | 72
1.34 | WW51.5 2013 | tmcconne | Index #24: Improved wording | 73
1.34 | WW51.5 2013 | tmcconne | Index #6: Improved wording | 74
1.34 | WW51.5 2013 | tmcconne | Index #1: Improved wording | 75
1.34 | WW51.5 2013 | tmcconne | Added Security standards, Index #295-301 | 76-82
1.34 | WW51.5 2013 | tmcconne | Removed Security Index #165 | 83
1.34 | WW51.5 2013 | tmcconne | Removed Security Index #189 | 84
1.34 | WW51.5 2013 | tmcconne | Added Security standards, Index #302-307 | 85-90
1.34 | WW51.5 2013 | tmcconne | Added FEV standard, Index #308 | 91
1.34 | WW51.5 2013 | tmcconne | Index #104: Improved wording | 92
1.35 | WW03.1 2014 tmccconne | tmcconne | Changed Simulation category owner to Mohamed Elmalaki
1.35 | WW03.1 2014 tmccconne | tmcconne | Froze "Index", "Category" and "Requirements" columns to help with usability (lost after 1.32 release)
1.35_v1 | WW03.5 2014 | tmcconne | Added Category #
1.35_v1 | WW03.5 2014 | tmcconne | Using "_v#" to indicate the standards have not changed.
1.35_v2 | WW04.7 2014 | tmcconne | Index #5: Added "CDC Intelpedia" as reference
1.35_v2 | WW04.7 2014 | tmcconne | Index #96, 97: Updated reference link to Emulation CoE
1.35_v2 | WW04.7 2014 | tmcconne | Index #95: Updated reference to DNV Emulation Lint page
1.35_v2 | WW04.7 2014 | tmcconne | Index #37, 38, 39, 259, 260, 261: Changed "Automation" value to "Auto", run 2.1.6.o
1.35_v2 | WW04.7 2014 | tmcconne | "Tracking, Field Values": added POR table
1.35_v2 | WW04.7 2014 | tmcconne | "Tracking, Field Values": Fixed definition of "SIP & HIP"
1.35_v2 | WW04.7 2014 | tmcconne | "Tracking, Field Values": Updated to "Auto", "Manual", "Future"
1.35_v2 | WW04.7 2014 | tmcconne | Restricted "Automation" column to "Auto", "Manual" and "Future"
1.35_v2 | WW04.7 2014 | tmcconne | Updated "Power Intent" category reference to "SoC Low Power Design"
1.35_v2 | WW04.7 2014 | tmcconne | Updated "Security" category references
1.35_v2 | WW04.7 2014 | tmcconne | Changed all "Q4'13" to "Q1'14" for "Tool ETA"
1.35_v3 | WW07.4 2014 | tmcconne | Index #51: Improved wording | 93
1.35_v3 | WW07.4 2014 | tmcconne | Index #127: Improved wording | 101
1.35_v3 | WW07.4 2014 | tmcconne | Index #176: Move from category DFt to VISA | 108
1.35_v3 | WW07.4 2014 | tmcconne | Index #265: Improved wording | 109
1.35_v3 | WW07.4 2014 | tmcconne | Index #56: Improved wording | 110
1.35_v3 | WW07.4 2014 | tmcconne | Index #57: Improved wording | 111
1.35_v3 | WW07.4 2014 | tmcconne | Index #62: Improved wording | 112
1.35_v3 | WW07.4 2014 | tmcconne | Index #63: Improved wording | 113
1.35_v3 | WW07.4 2014 | tmcconne | Index #65: Improved wording | 114
1.35_v3 | WW07.4 2014 | tmcconne | Index #66: Improved wording | 115
1.35_v3 | WW07.4 2014 | tmcconne | Index #67: Improved wording | 116
1.35_v3 | WW07.4 2014 | tmcconne | Index #68: Improved wording | 117
1.35_v3 | WW07.4 2014 | tmcconne | Index #70: Improved wording | 118
1.35_v3 | WW07.4 2014 | tmcconne | Index #71: Improved wording | 119
1.35_v3 | WW07.4 2014 | tmcconne | Index #72: Improved wording | 120
1.35_v3 | WW07.4 2014 | tmcconne | Index #167: Improved wording | 121
1.35_v3 | WW07.4 2014 | tmcconne | Category "SVTB": Updated all Reference links
1.35_v3 | WW07.4 2014 | tmcconne | Category "VISA": Updated all Reference links
1.35_v3 | WW07.4 2014 | tmcconne | Category "Security": Updated all Reference links
1.35_v3 | WW07.4 2014 | tmcconne | Index #270: Updated Reference link
1.35_v3 | WW07.4 2014 | tmcconne | Category "CDC": Updated all Reference links
1.35_v3 | WW07.4 2014 | tmcconne | Category "DFt": Updated all Reference links
1.35_v3 | WW07.4 2014 | tmcconne | Index #79: Updated Reference link
1.35_v3 | WW07.4 2014 | tmcconne | Category "Phys Des": Updated all Reference links to point to "SoC Design Kits" home page (temporary place holder)
1.35_v3 | WW07.4 2014 | tmcconne | Index #131: Updated Reference link to "SoC RTL Low Power Check" page
1.35_v3 | WW07.4 2014 | tmcconne | Category "RDL": Updated all Reference links
1.35_v3 | WW07.4 2014 | tmcconne | Category "Simulation": Added "VCS FAQ" for all missing Reference links
1.35_v3 | WW07.5 2014 | tmcconne | Moved "Comments" (old columns F, H, I) to the right side.
1.35_v4 | WW08.4 2014 | tmcconne | Updated ZQA rule links to match ZQA 14.06.0. Use "(multiple)" to indicate more than one ZQA rule
1.35_v5 | WW08.5 2014 | tmcconne | Change Phys Des category owner to Faran Rafiq
1.36 | WW12.1 2014 | tmcconne | Added Index #309: QuestaCDC input/output collateral delivered | 94
1.36 | WW12.1 2014 | tmcconne | Added Index #310: ONDA run is clean | 95
1.36 | WW12.1 2014 | tmcconne | Added Index #311: ONDA waivers delivered | 96
1.36 | WW12.1 2014 | tmcconne | Category "CDC": Removed Index #5, #21-43, #259-261 | 97
1.36 | WW12.1 2014 | tmcconne | Index #84: Standard wording does not change, linked documentation has IRR naming requirements | 98
1.36 | WW12.1 2014 | tmcconne | Added Index #312 in Power Intent | 99
1.36 | WW12.1 2014 | tmcconne | Added Index #312 in Power Intent | 100
1.36 | WW12.1 2014 | tmcconne | Removed Index #128, #129 | 102
1.36 | WW12.1 2014 | tmcconne | Index #306: Updated/merged wording | 102
1.36 | WW12.1 2014 | tmcconne | Removed Index #264 | 103
1.36 | WW12.1 2014 | tmcconne | Index #303: Updated/merged wording | 103
1.36 | WW12.1 2014 | tmcconne | Removed Index #58 (CLTAP) | 104
1.36 | WW12.1 2014 | tmcconne | Removed Index #59 (DFX, functionality) | 105
1.36 | WW12.1 2014 | tmcconne | Index #60: Improved wording; HIP only | 106
1.36 | WW12.1 2014 | tmcconne | Index #61: Improved wording | 107
1.36 | WW12.1 2014 | tmcconne | Index #4: Removed "with [ip_prefix" from wording | 122
1.36 | WW12.1 2014 | tmcconne | Removed Index #169 | 123
1.36 | WW12.1 2014 | tmcconne | Index #171: Improved wording | 124
1.36 | WW12.1 2014 | tmcconne | Removed Index #84 | 125
1.36 | WW12.1 2014 | tmcconne | Index #266: Improved wording (reference IP IRR drop naming requirement) | 126
1.36 | WW12.1 2014 | tmcconne | Index #133: Improved wording; explicit milestone requirements | 127
1.36 | WW12.1 2014 | tmcconne | Removed Index #136 | 128
1.36 | WW12.1 2014 | tmcconne | Removed Index #151 | 129
1.36 | WW12.1 2014 | tmcconne | Index #162: Applies to HIP only | 130
1.36 | WW12.1 2014 | tmcconne | Removed Index #269 | 131
1.36 | WW12.1 2014 | tmcconne | Index #295: Updated Reference link | 132
1.36 | WW12.1 2014 | tmcconne | Index #299: Improved wording | 133
1.36 | WW12.1 2014 | tmcconne | Index #299: Remove RTL0p0, RTL0p5 milestone requirements | 134
1.36 | WW12.1 2014 | tmcconne | Index #299: Modify reference link to point to documentation templates | 135
1.36 | WW12.1 2014 | tmcconne | Index #95: Updated wording; standard changed to "Yes" for POR | 136
1.36 | WW12.1 2014 | tmcconne | Added Index #314 in Emulation/FPGA | 137
1.36 | WW12.1 2014 | tmcconne | Removed Index #96 (Emulation Lintra checks) | 138
1.36 | WW12.1 2014 | tmcconne | Added new category: Back End Readiness. Said Moumaraf is category owner
1.36 | WW12.1 2014 | tmcconne | Renamed "Phys Des" category to "Physical Design Readiness". Oren Katzir is the cateory owner
1.36 | WW12.1 2014 | tmcconne | Updated category "Org Affiliation" to change CSG to IPG EIG
1.36 | WW12.1 2014 | tmcconne | Index #294: Changed to "No" for POR due to Caliber not being a POR tool for IP
1.36 | WW12.1 2014 | tmcconne | Changed "Power Lint" category owner to "Vadivel Ramalingam"
1.36 | WW12.1 2014 | tmcconne | Index #95, 97, 314 (Emulation/FPGA): Updated Reference link
1.36 | WW12.1 2014 | tmcconne | Added "POLO" and "PROD" columns to support HIP-only standards
1.36 | WW12.1 2014 | tmcconne | Index #20: Improved wording to emphasize documentation
1.36 | WW12.1 2014 | tmcconne | Index #8, #17, #20: Added Reference link
1.36 | WW12.1 2014 | tmcconne | Index #98 (FEV): Improved wording
1.36 | WW12.1 2014 | tmcconne | Index #99 (FEV): Improved wording
1.36 | WW12.1 2014 | tmcconne | Index #100 (FEV): Improved wording
1.36 | WW12.1 2014 | tmcconne | Index #101 (FEV): Improved wording
1.36 | WW12.1 2014 | tmcconne | Index #102 (FEV): Improved wording
1.36 | WW12.1 2014 | tmcconne | Index #308 (FEV): Improved wording
1.36 | WW12.1 2014 | tmcconne | Removed "Rationale" and "Comments" columns from Categories tab. No longer relevant
1.37 | WW12.2 2014 | tmcconne | Index #197: Updated Reference link to point to IPDS Sharepoint
1.37 | WW12.2 2014 | tmcconne | Index #198: Updated Reference link to point to IPDS Sharepoint
1.37 | WW12.2 2014 | tmcconne | Index #199: Updated Reference link to point to IPDS Sharepoint
1.37 | WW12.2 2014 | tmcconne | Category Simulation, Index #179: Improved wording | 139
1.37 | WW12.2 2014 | tmcconne | Category Simulation, Index #181: Improved wording | 140
1.37 | WW12.2 2014 | tmcconne | Category Simulation, Index #182: Improved wording | 141
1.37 | WW12.2 2014 | tmcconne | Category Simulation, Index #183: Improved wording | 142
1.37 | WW12.2 2014 | tmcconne | Category Simulation, Index #184: Improved wording | 143
1.37 | WW12.2 2014 | tmcconne | Category Simulation, Remove Index #186 | 144
1.37 | WW12.2 2014 | tmcconne | Category Simulation, Index #187: Improved wording | 145
1.37 | WW12.2 2014 | tmcconne | Category Simulation, Remove Index #188 | 146
1.37 | WW12.2 2014 | tmcconne | Category Simulation, Remove Index #190 | 147
1.37 | WW12.2 2014 | tmcconne | Category DFt, Index #265: Improved wording (include "ISAF flow") | 148
1.37 | WW12.2 2014 | tmcconne | Category DFt, New standard #315 (IP info file) | 149
1.37 | WW12.2 2014 | tmcconne | Category RTL+Lint, New standard #316 (CTECH) | 150
1.37 | WW12.2 2014 | tmcconne | Category FEV: Index #98: Improved wording
1.37 | WW12.2 2014 | tmcconne | Category FEV: Index #103: Improved wording
1.38 | WW12.3 2014 | tmcconne | Index #168: (Fuse Pull Completion Message format) moved to Category RDL
1.38 | WW12.3 2014 | tmcconne | Category VISA: Updated all Reference links to use "visa-it" per-rule links
1.38 | WW12.3 2014 | tmcconne | Category Build & Run: Russ Jackson is Category Owner
1.38 | WW12.3 2014 | tmcconne | Index #181: Change "serial clk" to "serial clock" (not a signal name, this is a description)
1.38 | WW12.3 2014 | tmcconne | Category RTL+Lint: Index #316 (CTECH Methodology): SIP Only
1.38 | WW12.3 2014 | tmcconne | Category FEV: Index #98: Improved wording
1.38 | WW12.3 2014 | tmcconne | Category FEV: Index #99: Improved wording
1.38 | WW12.3 2014 | tmcconne | Category FEV: Index #100: Improved wording
1.38 | WW12.3 2014 | tmcconne | Category FEV: Index #101: Changed wording ("undriven to 0" becomes "undriven to constant")
1.38 | WW12.3 2014 | tmcconne | Category FEV: Index #102: Improved wording
1.38 | WW12.3 2014 | tmcconne | Category FEV: Removed Index #103 (unmapped key points)
1.38 | WW12.3 2014 | tmcconne | Category FEV: Index #308: Improved wording
1.39 | WW13.2 2014 | tmcconne | Removed RTL0p7 column, based on Velocity PLC
1.39 | WW13.2 2014 | tmcconne | Category CDC: Index #309, 310, 311: Required in RTL0p5, based on Velocity PLC
1.39 | WW13.2 2014 | tmcconne | Category Collage: Index #51: Required in RTL0p0, based on Velocity PLC
1.39 | WW13.2 2014 | tmcconne | Category Review: Index #133: Each milestone per HAS, based on Velocity PLC
1.39 | WW13.2 2014 | tmcconne | Category SV TB: Index #214: Each milestone per HAS, based on Velocity PLC
1.39 | WW13.2 2014 | tmcconne | Category SV TB: Index #216: Higher quality at RTL0p8 (85%), based on Velocity PLC. Improved wording
1.39 | WW13.2 2014 | tmcconne | Category VISA: All requirements at RTL0p5, based on Velocity PLC.
1.39 | WW13.2 2014 | tmcconne | Category Phys Design Enabling: Remove Index #290, duplicate of #293
1.39 | WW13.2 2014 | tmcconne | Category Build & Run: Index #18, change Automation to "Manual"
1.39 | WW13.2 2014 | tmcconne | Updated "Automation" column based on feedback from ZirconQA team
1.40 | WW13.2 2014 | tmcconne | Remove "Tool" column. ZirconQA (ZQA) tracks all checks
1.40 | WW13.2 2014 | tmcconne | Remove "Tool ETA" column. Deprecated, was originally a planning tool
1.40 | WW13.2 2014 | tmcconne | Support only "Manual" and "Auto" for Automation (removed "Future", changed to "Manual")
1.41 | WW13.4 2014 | tmcconne | Category Build & Run: Remove Index #18 (duplicate of #10)
1.41 | WW13.4 2014 | tmcconne | Category Build & Run: Index #19: Improved wording
1.41 | WW13.4 2014 | tmcconne | Remove "POLO" and "PROD" until standards exist (none exist right now)
1.41 | WW13.4 2014 | tmcconne | Category Emulation/FPGA: Index #95, 97, 314: Fixed Reference links
1.41 | WW13.4 2014 | tmcconne | Moved "Tracking, Field Values", "Further review" and "Additional Detail" to the end for better readability
1.41 | WW13.4 2014 | tmcconne | Category Phys Design Enabling: Index #277: Improved wording to emphasize "MCO" and "DFX" as part of constraints
1.41 | WW13.4 2014 | tmcconne | Category Phys Design Enabling: Index #277: Improved wording to emphasize converged PVT target
1.41 | WW13.4 2014 | tmcconne | Index #247: Move category from "Security" to "VISA"
1.41 | WW13.4 2014 | tmcconne | Index #185: Move category from "Security" to "Power Intent"
1.41 | WW13.4 2014 | tmcconne | Category Documentation: Index #94: Improved wording to emphasize verification per HAS
1.41 | WW13.4 2014 | tmcconne | Category Build & Run: Index #10: ACE required libraries at RTL0p0 (align with #11)
1.41 | WW13.4 2014 | tmcconne | Category Build & Run: Remove Index #13: Duplicate of #11
1.41 | WW13.4 2014 | tmcconne | Category Build & Run: Index #14: Add "Clean" at RTL0p0 (shell only)
1.41 | WW13.4 2014 | tmcconne | Category Build & Run: Index #44: corekit verified at RTL0p0 (shell only)
1.41 | WW13.4 2014 | tmcconne | Category Build & Run: Index #46: corekit verified at RTL0p0 (shell only)
1.41 | WW13.4 2014 | tmcconne | Category Collage: Fixed multiple Tool Rule links
1.41 | WW13.4 2014 | tmcconne | Category DFt: Fixed multiple Tool Rule links
1.41 | WW13.4 2014 | tmcconne | Category Physical Design Enabling: Jared Jones is Category Owner
1.41 | WW13.4 2014 | tmcconne | Category Power Intent: Index #302: Fixed misspelled word
1.41 | WW13.4 2014 | tmcconne | Index #79, 90, 302, 303, 304, 305, 306, 307: Manual checking
1.41 | WW13.4 2014 | tmcconne | Category Build & Run: Index #16: Reference link: Use Verification Reference
1.41 | WW13.4 2014 | tmcconne | Category RTL + Lint: Index #3, #4, #47: Reference link: Use generic "Lintra" link
1.41 | WW13.4 2014 | tmcconne | Category Simulation: Index #79: Reference link: Use Verification Reference
1.41 | WW13.4 2014 | tmcconne | Category Power Intent: Index #185: Reference link: Use Verification Reference
1.42 | WW13.5 2014 | tmcconne | Category Physical Design Enabling: Index #124: Updated timing targets
1.42 | WW13.6 2014 | tmcconne | Category Emulation/FPGA: New category owner, Jai Kumar
1.42 | WW13.6 2014 | tmcconne | Category Simulation: Index #181, 182: Add RTL0p5 requirements to support "early DFX" from Velocity PLC
1.42 | WW13.6 2014 | tmcconne | Category DFt: Index #69, 70, 71, 72: Add RTL0p5 requirements to support "early DFX" from Velocity PLC

## Tracking, Field Values
IP Status | Definition
Not Done | This item is not complete (assumption is that it is in progress)
Done | This item is complete
N/A | This item is not applicable to the IP
SoC Decision | Definition
Not Done | This item is not complete (assumption is that it is in progress)
Done | This item is complete
Exception Request | This item is not complete and the IP provider is requesting a exception / waiver for the item
Waive | This item is not complete, the IP provider was granted an exception / waiver by the SoC
N/A | This item is not applicable to the IP
Automation | Definition
Auto | Automated checking exists, listed in "Tool" and "Tool Rule" columns
Manual | No automated checking exists
Applicability | Definition
SIP Only | Requirement applies only to Soft IP
HIP Only | Requirement applies only to Hard IP
SIP & HIP | Requirement applied to both Soft and Hard IP
POR | Definition
Yes | Requirement has been officially approved
No | Requirement has not been officially approved
Next Rule #
317

## Further review
Category | Requirement | RTL 0p0 | RTL 0p5 | RTL 0p7 | RTL 0p8 | RTL 1p0 | Maturity | Check | Tool | Exists? | Source | Activity | Type | DNV Bucket | Comments | Type of Test | Cat Owner | Orig Category | Sub-Category | POR status | Collateral File
Verification | Clock waveform matches CCDO |  |  |  | Matches | Matches | 0p8 | Manual |  |  | DICEE v1.11 (WW24.1'13 markup) |  | Review |  | Convergence? | IP Std. Compliance | Joel Feldman | Verification |  | Review | https://sharepoint.amr.ith.intel.com/sites/phtdesign/spcm/BXTSoCPVClockMethodology/BXT_SOC_clock_spreadsheet.xlsx -> BXT https://sharepoint.amr.ith.intel.com/sites/phtdesign/spcm/CRCSoCPVClockMethodology/CRC_clock_spreadsheet.xlsx -> CRC
SV TB | IP VC configuration is reusable | [5 empty] | 0p5 | Manual |  |  | DNV RTL 0p5 In-Out Criteria | Evaluation | Collateral Check | Val | (Should extending from ovm_scoreboard, instantiated in tb environment) | IP SoC Integration | Joel Feldman | General |  | POR
SV TB | Strap configuration is done through dynamic class objects |  | Verified | Verified | Verified | Verified | 0p5 | Auto | ZQA |  | Zircon rules_POR_v1.0 (WW24.5'13 markup) |  | Review |  | Manual ZQA exists | IP SoC Integration | Hassan Shehab | Verification |  | POR
Documentation | sub-IPs are documented with version used, if they are intended to be "common" or "local", and if local, should be uniquified. | [5 empty] | 0p5 | Partial | ZQA |  | DNV RTL 0p5 In-Out Criteria |  | Review | Integ | (Uniquified is ZQA rule) | IP Std. Compliance | Susann Flowers
SV TB | VC configuration is reusable |  | Verified | Verified | Verified | Verified | 0p7 | Manual |  |  | Zircon rules_POR_v1.0 (WW24.5'13 markup) |  | Review |  |  | IP SoC Integration | Joel Feldman | Verification |  | POR
Directory Structure | Need directory structure/file requirements/discipline/checking
Directory Structure | Unused and duplicate rdl, ral files should be removed from the IP - as they are creating confusion for debugging and documentation | [5 empty] | 0p8 | Manual |  |  | DICEE v1.11 (WW24.1'13 markup) |  | Collateral Check |  | Project specific | IP SoC Integration | Hassan Shehab | General | RDL | POR | *.rdl, *ral_env.svh, *regs_ral_env.svh, *regs.svh
Phys Des | Timing interface modeling for both max (critical path) analysis and min (race) analysis is required. This file should include the process skew, voltage, temperature, and units for time¦voltage¦capacitance. Should include input slope requirements & allowed output min¦max capacitance. | [5 empty] | 0p8 | Manual |  |  | DICEE v1.11 (WW24.1'13 markup) |  | Collateral Check |  | Timing methodology? | IP SoC Integration | Joel Feldman | Verification |  | Review | max.lib, min.lib, max.ldb, min.ldb
SV TB | SV TB Lint
SV TB | Tests written |  |  | 25% tests written | 75% tests written | 100% tests written | 1p0 | Manual |  |  | Converged Checklist Rev 0.91 WW22.2 markup |  | Review |  | How does this relate to regression? | IP Std. Compliance | Joel Feldman | Verification |  | Review
SV TB | IP RTL: IP-level test coding > 50% vs. estimated final targets (IP VAL 1.0) | [5 empty] | 0p5 | Auto |  |  | VICEE v1.10 WW27 markup | Evaluation | Quality Review | IP Qual | Specific target; how to calculate? DNV: Beyond PLC target? | IP SoC Integration | Joel Feldman | General |  | Review
SV TB | IP RTL: IP-level test coding > 80% vs. estimated final targets (IP VAL 1.0) | [5 empty] | 0p8 | Auto |  |  | VICEE v1.10 WW27 markup | Evaluation | Quality Review |  | Actual value? | IP SoC Integration | Joel Feldman | General |  | Review
SV TB | SAOLA interrupt manager support | [5 empty] | 0p5 | Auto | ZQA | Yes | Zircon rules_POR_v1.0 (WW24.5'13 markup) |  | Only lives at SoC | Val |  | IP SoC Integration | Joel Feldman | Verification |  | POR
Review | SDL Design review |  |  |  | S2 | S3 | 0p8 | Manual |  |  | Converged Checklist Rev 0.91 WW22.2 markup |  | Need an RDL check |  |  | IP Std. Compliance | Susann Flowers | General | Security | Review
Documentation | Review Place and route guidelines in "CRC-BXT 0.8 Signal Guidelines" worksheet | [5 empty] | 0p8 | Manual |  |  | DICEE v1.11 (WW24.1'13 markup) |  | Review |  | Visa methodology? | IP Std. Compliance | Susann Flowers | DFx | VISA | Review
Documentation | Review security guidelines in "CRC-BXT 0.8 Signal Guidelines" worksheet | [5 empty] | 0p8 | Manual |  |  | DICEE v1.11 (WW24.1'13 markup) |  | Review |  | Visa methodology? | IP Std. Compliance | Susann Flowers | DFx | VISA | Review
Documentation | Review timing guidelines in "CRC-BXT 0.8 Signal Guidelines" worksheet | [5 empty] | 0p8 | Manual |  |  | DICEE v1.11 (WW24.1'13 markup) |  | Review |  | Visa methodology? | IP Std. Compliance | Susann Flowers | DFx | VISA | Review
| Review Misc guidelines in "CRC-BXT 0.8 Signal Guidelines" worksheet | [5 empty] | 0p8 | Manual |  |  | DICEE v1.11 (WW24.1'13 markup) |  | Review |  | Visa methodology? | IP Std. Compliance | Joel Feldman | DFx | VISA | Review
| Review coverage quality guidelines in "CRC-BXT 0.8 Signal Guidelines" worksheet | [5 empty] | 0p8 | Manual |  |  | DICEE v1.11 (WW24.1'13 markup) |  | Review |  | Visa methodology? | IP Std. Compliance | Joel Feldman | DFx | VISA | Review
| Review all properties for each Fuse Field 1) Please use Virtual Fuses wherever possible 2) For Secure Fuses(keys, certain debug features etc) please review the Distribution and Access Control properties to ensure they meet security requirements for these assets 3) Review Default Value field to ensure this is a safe value so that an un-fused part can function. | [5 empty] | 0p8 | Manual |  |  | DICEE v1.11 (WW24.1'13 markup) |  | Review |  |  | IP SoC Integration | Joel Feldman | General | RDL | POR
DFt | Pull up Scan Control signals (fscan_*) to IP Top. DFx team will make connection from IP Top to Cluster DFx Unit (CDU) in SOC. This is for SIP and HIP. | [5 empty] | 0p8 | Manual |  |  | DICEE v1.11 (WW24.1'13 markup) |  | Collateral Check |  | Scan methodology? | IP SoC Integration | Joel Feldman | DFx |  | Review
Documentation | Production level design documentation | [5 empty] | 1p0 | Manual |  |  | Converged Checklist Rev 0.91 WW22.2 markup |  | Review |  | Data Book. Confidentiality? | IP Std. Compliance | Susann Flowers | Documentation |  | Review
| 40% features enabled | [5 empty] | 0p5 | Manual |  |  | Converged Checklist Rev 0.91 WW22.2 markup |  | Review |  | Not measurable | IP Std. Compliance | Joel Feldman | Verification |  | Review
| All IP specific (security, etc.) exclusions identified |  |  |  | Identified | Identified | 0p8 | Manual |  |  | DICEE v1.11 (WW24.1'13 markup) |  | Review |  | Scan methodology? | IP SoC Integration | Joel Feldman | DFx |  | Review
| All latches meet SoC scan design rules |  |  |  | Verified | Verified | 0p8 | Manual |  |  | DICEE v1.11 (WW24.1'13 markup) |  | Review |  | Latches are deprecated ( https://sharepoint.amr.ith.intel.com/sites/phtdesign/bxtrtl/RTLExecutionDocs/DFT_VT_IP_requirements_ww11'13.pptx ) | IP Std. Compliance | Joel Feldman | DFx |  | Review
| Check that Average Power Spreasheet assumptions are consistent with RTL being delivered - Setup meeting with Power Domain Owner |  |  |  | Reviewed | Reviewed | 0p8 | Manual |  |  | DICEE v1.11 (WW24.1'13 markup) |  | Collateral Check |  | Documentation POR? | IP Std. Compliance | Hassan Shehab | Power |  | Review | HAS
Phys Des | Clamp file must exist |  |  | Verified | Verified | Verified | 0p7 | Auto |  |  | Zircon rules_POR_v1.0 (WW24.5'13 markup) |  | Collateral Check |  | No converged requirement | IP SoC Integration | Hassan Shehab | RTL |  | Review
| Cross clock on same output lane not allowed | [5 empty] | 0p8 | Auto |  |  | DICEE v1.11 (WW24.1'13 markup) |  | Collateral Check |  | Visa methodology? | IP Std. Compliance | Hassan Shehab | DFx | VISA | Review
Build | CTECH map file contains the cells from the target library |  |  | Verified | Verified | Verified | 0p7 | Manual |  |  | Zircon rules_POR_v1.0 (WW24.5'13 markup) |  | Collateral Check |  | Changes with CTECH_LIB | IP SoC Integration | Hassan Shehab | General | Synthesis | Review
| Each IP is required to provide a co-location wrapper where all the memories are instantiated that sits within the IP, but outside of the functional RTL. Please provide the path to this co-location wrapper. CRC: This is not a hard requirement since CRC is being seeded by ANN. BXT: This is a hard requirement. |  |  |  | Verified | Verified | 0p8 | Manual |  |  | DICEE v1.11 (WW24.1'13 markup) |  | Collateral Check |  | BIST? | IP SoC Integration | Hassan Shehab | DFx |  | Review
Phys Des | Synthesis timing |  | Within 25% | Within 25% | Within 20% (DICEE 10%) | Meets timing | 0p5 | Manual |  |  | Converged Checklist Rev 0.91 WW22.2 markup |  | Effort to close timing vs. 100% functional | Phys |  | IP Std. Compliance | Joel Feldman | General | Synthesis | POR
Phys Des | Minimum clock uncertainty is met as a percentage of clock period + some flat number |  | Verified | Verified | Verified | Verified | 0p5 | Auto | ZQA |  | Zircon rules_POR_v1.0 (WW24.5'13 markup) |  | Need an actual number |  | No converged requirement | IP Stand Alone | Joel Feldman | General | Synthesis | ZQR
SV TB | The monitor contains a coverage collector on the interface timing/protocol |  | Verified | Verified | Verified | Verified | 0p5 | Auto | ZQA |  | Zircon rules_POR_v1.0 (WW24.5'13 markup) |  | Waiting on Joel's feedback |  | Manual ZQA exists | IP SoC Integration | Joel Feldman | Verification |  | POR
SV TB | The monitor contains all the cycle-based protocol/timing checks |  | Verified | Verified | Verified | Verified | 0p5 | Auto | ZQA |  | Zircon rules_POR_v1.0 (WW24.5'13 markup) |  | Waiting on Joel's feedback |  | Manual ZQA exists | IP SoC Integration | Joel Feldman | Verification |  | POR
Documentation | Major data and control interfaces specified | [5 empty] | 0p0 | Manual |  |  | Converged Checklist Rev 0.91 WW22.2 markup |  | Anything specific beyond other reqs? |  | EAD Percentage? | IP Std. Compliance | Susann Flowers | Documentation |  | Review
DFt | IPs to provide Chassis Tap Tool (CTT) xml file describing the tap instantiated within the IP. | [5 empty] | 0p8 | Manual |  |  | DICEE v1.11 (WW24.1'13 markup) |  | Collateral Check |  | Note that this is to help provide the IR/DR information in system RDL format. If the IP team prefers they can just provide the system RDL in the same format produced by the CTT. | IP SoC Integration | Hassan Shehab | DFx |  | Review | CTT Tool is here. There are links to the tool and instructions on how to use it. https://sharepoint.amr.ith.intel.com/sites/MDGArchMain/Converged/DFxChassisWG/SoC%20DFx/Forms/AllItems.aspx?RootFolder=%2fsites%2fMDGArchMain%2fConverged%2fDFxChassisWG%2fSoC%20DFx%2fDFx%20Fabrics%20%28TAP%2c%20etc.%29%2fTAP%2fz_Chassis%20TAP%20Tool&FolderCTID=0x01200032EF0B3AEF55E04F9766D93D71CF11B4
DFt | MBIST_CTRL v2.0 (if applicable) | [5 empty] | 0p8 | Manual |  |  | DICEE v1.11 (WW24.1'13 markup) |  | SoC or IP? |  | BIST? | IP SoC Integration | Mukesh Mishra | DFx |  | Review
DFt | MBIST_WTAP v2.0 (if applicable) | [5 empty] | 0p8 | Manual |  |  | DICEE v1.11 (WW24.1'13 markup) |  | SoC or IP? |  | BIST? | IP SoC Integration | Mukesh Mishra | DFx |  | Review
DFt | RTDR_CTRL v1.5 (if applicable) | [5 empty] | 0p8 | Manual |  |  | DICEE v1.11 (WW24.1'13 markup) |  | SoC or IP? |  | BIST? | IP SoC Integration | Mukesh Mishra | DFx |  | Review
| Minimize the use of "fill-lanes" | [5 empty] | 0p8 | Auto |  |  | DICEE v1.11 (WW24.1'13 markup) |  | Review |  | Visa methodology? | IP Std. Compliance | Hassan Shehab | DFx | VISA | Review
| No static signals observability on static signals, ie. no signals that are tied off | [5 empty] | 0p8 | Auto |  |  | DICEE v1.11 (WW24.1'13 markup) |  | Review |  | Visa methodology? | IP Std. Compliance | Joel Feldman | DFx | VISA | Review
DFt | GLS scan: one test passing |  |  |  | Passing | Passing | 0p8 | Manual |  |  | Converged Checklist Rev 0.91 WW22.2 markup |  | Review |  | CSE feedback: SoC role | IP Std. Compliance |  |  |  | Review
SV TB | Statement coverage |  |  |  | 85% | 95% | 0p8 | Auto |  |  | Converged Checklist Rev 0.91 WW22.2 markup |  | Collateral Check |  | No converged requirement | IP Std. Compliance |  |  |  | Review
VISA | No faster than 400 MHz - divide if greater than 400MHz - review with Visa owner if faster | [5 empty] | 0p8 | Auto | Calibre |  | DICEE v1.11 (WW24.1'13 markup) |  | Collateral Check |  | VISA WG feedback | IP Std. Compliance |  |  |  | Review
Note on B3: Thomas McConnell: Owner? Tony Jacobs? Dave Bertinetti? What to check? Reusable Scoreboards & Checkers available by 0p5.
Note on B4: Thomas McConnell: Duplicate to having sRDL strap
Note on B34: Thomas McConnell: Joel to review: Interface?
Note on B35: Thomas McConnell: Joel to review…

## Additional Detail
Category | Requirement | RTL 0p0 | RTL 0p5 | RTL 0p7 | RTL 0p8 | RTL 1p0 | Check | Tool | Exists? | Comments | Source | Activity | Maturity | Type | DNV Bucket | Type of Test | Cat Owner | Orig Category | Sub-Category | POR status | Collateral File
Collage | CoreKit delivered to hook up all interfaces. Functional adhoc signals closed, DFx adhoc signals closed. Exceptions not covered by Corekit docuemented in Integ Guide and reviewed by Integ team. Corekit validated | [5 empty] | Auto |  |  |  | DICEE v1.11 (WW24.1'13 markup) |  | 0p8 | Collateral Check |  | IP Std. Compliance | Mukesh Mishra | RTL |  | POR
Collage | CoreKit. Boundary Scan v1.5 (if applicable) | [5 empty] | Auto |  |  | Version? | DICEE v1.11 (WW24.1'13 markup) |  | 0p8 | Collateral Check |  | IP SoC Integration | Mukesh Mishra | DFx |  | Review
Collage | CoreKit. JTAG Interface v1.0 (if applicable) | [5 empty] | Auto |  |  | Version? | DICEE v1.11 (WW24.1'13 markup) |  | 0p8 | Collateral Check |  | IP SoC Integration | Mukesh Mishra | DFx |  | Review
Collage | CoreKit. Scan Interface v2.1 | [5 empty] | Auto |  |  | Version? | DICEE v1.11 (WW24.1'13 markup) |  | 0p8 | Collateral Check |  | IP SoC Integration | Mukesh Mishra | DFx |  | Review
Collage | CoreKit. VISA v1.0 | [5 empty] | Auto |  |  | Version? VISA methodology? | DICEE v1.11 (WW24.1'13 markup) |  | 0p8 | Collateral Check |  | IP SoC Integration | Mukesh Mishra | DFx | VISA | Review
Collage | CoreKit. VISA_CFG v1.0 | [5 empty] | Auto |  |  | Version? VISA methodology? | DICEE v1.11 (WW24.1'13 markup) |  | 0p8 | Collateral Check |  | IP SoC Integration | Mukesh Mishra | DFx |  | Review
Simulation | If IPP chooses to run GLS - it has to be at least 0-delay non-timed back annotated version of GLS that is run at the IP level using the set of tests that exercise initialization and basic protocols. |  |  |  | Reviewed | Reviewed | Auto |  |  | GLS is currently POR | DICEE v1.11 (WW24.1'13 markup) |  | 0p8 | Collateral Check |  | IP Std. Compliance | Joel Feldman | RTL |  | POR
Simulation | If IPP chooses to run XPROP - the IP provider needs to enable XPROP on the RTL model and run the DOA test and the Level0 tests through XPROP. | [5 empty] | Auto |  |  | XPROP not POR | DICEE v1.11 (WW24.1'13 markup) |  | 0p8 | Collateral Check |  | IP Std. Compliance | Joel Feldman | RTL |  | Review
Build | If upgrade needed - Any data change will need to be validated at IP level with tool versions used in previous IP release integrated into the SoC model | [5 empty] | Manual |  |  |  | DICEE v1.11 (WW24.1'13 markup) |  | 0p8 | Review |  | IP Std. Compliance | Joel Feldman | General |  | POR
Build | If upgrade needed - Communicate reasons and intent to upgrade(with tool name/version) to the tool experts in SoC teams | [5 empty] | Manual |  |  | Integration guide | DICEE v1.11 (WW24.1'13 markup) |  | 0p8 | Review |  | IP Std. Compliance | Joel Feldman | General |  | POR
Build | If upgrade needed - Identify exact list of reasons | [5 empty] | Manual |  |  | Integration guide | DICEE v1.11 (WW24.1'13 markup) |  | 0p8 | Review |  | IP Std. Compliance | Joel Feldman | General |  | POR
Build | If upgrade needed - make sure new tool version is 100% backward compatible with previous version used | [5 empty] | Manual |  |  | DA decision | DICEE v1.11 (WW24.1'13 markup) |  | 0p8 | Review |  | IP Std. Compliance | Joel Feldman | General |  | Review
Build | If upgrade needed - Wait for feedback from SoC team for Green Flag on the upgrade - IP Office in loop | [5 empty] | Manual |  |  | Integration guide | DICEE v1.11 (WW24.1'13 markup) |  | 0p8 | Review |  | IP SoC Integration | Joel Feldman | General |  | POR
Documentation | Integration guide should have list of active and top-level RDL and RAL files along with their paths | [5 empty] | Auto |  |  | Project specific | DICEE v1.11 (WW24.1'13 markup) |  | 0p8 | Review |  | IP SoC Integration | Susann Flowers | General | RDL | POR | Integration Guide
Review | IP Doc: Forces/injections needed inside the IP for RESET are documented/reviewed | [5 empty] | Manual |  |  | Verification reference, not "any" (Part of integration guide?) | VICEE v1.10 WW27 markup | Evaluation | 0p5 | Quality Review | IP Qual | IP SoC Integration | Susann Flowers | Documentation | RESET | Review | Integration Guide
Review | IP Doc: Major bugs and restrictions on testing 0.5 features at the integration level are documented/reviewed | [5 empty] | Manual |  |  | Release Notes (should all bugs be part of integration guide) | VICEE v1.10 WW27 markup | Evaluation | 0p5 | (Integration Guide section?) | IP Qual | IP SoC Integration | Susann Flowers | Documentation |  | POR | Integration Guide
Documentation | IP Doc: Major bugs and restrictions on testing 0.8 features at the integration level are documented/reviewed | [5 empty] | Manual |  |  | Verification reference or Integration guide, not "any" (Any documenation format acceptable - may be part of integration guide) | VICEE v1.10 WW27 markup | Evaluation | 0p8 | (Integration Guide section?) |  | IP SoC Integration | Susann Flowers | Documentation |  | POR | Integration Guide
Documentation | IP Doc: Major bugs and restrictions on testing 1.0 features at the integration level are documented/reviewed | [5 empty] | Manual |  |  | Verification reference or Integration guide, not "any" (Any documenation format acceptable - may be part of integration guide) | VICEE v1.10 WW27 markup | Evaluation | 1p0 | (Integration Guide section?) |  | IP SoC Integration | Susann Flowers | Documentation |  | POR | Integration Guide
Review | IP Doc: Reusable Test Island methods/knobs for RESET acceleration are documented/reviewed | [5 empty] | Manual |  |  | Want a "fast simulation" section in documentation | VICEE v1.10 WW27 markup | Evaluation | 0p5 | Quality Review | Val | IP SoC Integration | Susann Flowers | Documentation | RESET | POR
Documentation | IP Doc: Reusable Test Island methods/knobs for RESET acceleration are documented/revisited | [5 empty] | Manual |  |  | Want a "fast simulation" section in documentation | VICEE v1.10 WW27 markup | Evaluation | 0p8 | Quality Review |  | IP SoC Integration | Susann Flowers | Documentation | RESET | POR
Documentation | IP Doc: Reusable Test Island methods/knobs for RESET acceleration are documented/revisited | [5 empty] | Manual |  |  | Want a "fast simulation" section in documentation | VICEE v1.10 WW27 markup | Evaluation | 1p0 | Quality Review |  | IP SoC Integration | Susann Flowers | Documentation | RESET | Review